## Sheet1
| id | issuetype | description | summary | created | cluster
732581 | 12712734 | Epic |  | Improve Events page | 2017-09-21 08:06
732582 | 12712493 | Story | There is a difference between how searches in the main RHD site return results for site searches and how the blog does. Blog searches should be expanded to match the main RHD site as best they can. Example: This search returns more extensive results for Microservices: [RHD Search¦https://developers.redhat.com/blog/?s=microservices] ... than this one: [Blog Search¦https://developers.redhat.com/search/?q=microservices] The search in the blog only returns results by tag. At the very least, categories should searched, as should titles, and any available meta content, if possible. | Blog - Expand Blog General Search Functionality | 2017-09-20 09:20
732583 | 12712397 | Story | Table of content would be auto generated. User can select which Header formats are included in the ToC. Done: I would be able to immediately and easily import this document: http://redhat-sectech.gitlab.io/defensive-coding-guide/ | create new drupal template for very long documents | 2017-09-19 18:29
732584 | 12712396 | Story | h2. Requirements A content creator is able to select a markup language (Asciidoc or Markdown) from the list of available accepted editors. They are then able to enter content in the selected markup language and have it display correctly on the newly created page once saved. h2. Design h2. Stakeholders UX: N/A VD: N/A Eng: h2. Acceptance Criteria {noformat} Given: A user with the Content Creator Role creates new a new content page Then the text editor has a drop-down for Markdown And the text editor has a drop-down for Asciidoc Given: A user with the Content Creator Role creates new a new content page And the user has selected either Markdown or Asciidoc for the editor Then the WYSIWYG editor disappears, leaving a textbox to enter text Given A user with the Content Creator Role creates new a new content page using a markup language And the page has been saved Then the saved content will look like the markup has been processed and displayed as HTML {noformat} h2. Tasks * New modules are installed to use asciidoc and markdown * New text editors are created use each markup language * Content Creator permissions are updated to allow the new text editors | accept/import markup languages directly into drupal | 2017-09-19 18:28
732585 | 12712360 | Story | Apply an image compression mode and/or plugin to improve page speed. This tracker will be used to indicate how compression files before and after implementation, to aid in picking out the best way of handling the task. This is one task associated with this issue: [DEVELOPER-3995¦https://issues.jboss.org/browse/DEVELOPER-3995] | Blog - Apply better image compression | 2017-09-19 11:52
732586 | 12712168 | Story | Details to follow | Add redirect links and update tests for "Thank you page" media downloads | 2017-09-18 11:21 | 742
732587 | 12712152 | Epic | h2. Requirements [Product Downloads - CTA Use Cases & Requirements ¦https://docs.google.com/document/d/1m1WljXUSM8EonxaFKtDTmysxrWUnssH1PiShKZ6Mz1o/edit#] h2. Design h2. Stakeholders UX: [~gdoyle-1] VD: [~jcobb@redhat.com] Eng: [~ldary24] h2. Acceptance Criteria [Product Downloads Scenarios Doc¦https://docs.google.com/a/redhat.com/document/d/13FBi0Ths9vq71KZhSFAo8Yx1DEf18LxZJIomlzh4N18/edit?usp=sharing] h3. Feature I: Product Overview Page Downloads h3. Scenario 1 Scenario: User navigates to CDK’s product downloads page using Mac OS Given I am on CDK’s product download page Then underneath the download button, add “for Mac” after the version. h3. Scenario 2 Scenario: User downloads CDK using Mac OS Given I am on CDK’s product download page And I am using Mac OS When I select the download button Then download the Mac OS version of CDK (Filename ends in .dmg or contains “mac, “osx”, or “darwin”). h3. Scenario 3 Scenario: User navigates to CDK’s product downloads page using Windows OS Given I am on CDK’s product download page Then underneath the download button, display “for Windows” after the version. h3. Scenario 4 Scenario: User downloads CDK using Windows OS Given I am on CDK’s product download page And I am using Windows OS When I select the download button Then download the Windows OS version of CDK (Filename ends in .exe). h3. Scenario 5 Scenario: User navigates to CDK’s product downloads page using Linux OS Given I am on CDK’s product download page Then display “Install CDK” instead of “Download” in the CTA And underneath the button, display “for Linux” after the version. h3. Scenario 6 Scenario: User downloads CDK using Linux OS Given I am on CDK’s product download page And I am using Linux OS When I select the “Install CDK” button Then bring me to CDK’s Hello World! Page. h3. Scenario 7 Scenario: User navigates to DevSuite’s product downloads page using Mac OS Given I am on DevSuite’s product download page Then underneath the download button, add “for Mac” after the version. h3. Scenario 8 Scenario: User downloads DevSuite using Mac OS Given I am on DevSuite’s product download page And I am using Mac OS When I select the download button Then download the Mac OS version of DevSuite. h3. Scenario 9 Scenario: User navigates to DevSuite’s product downloads page using Windows OS Given I am on DevSuites product download page Then underneath the download button, display “for Windows” after the version. h3. Scenario 10 Scenario: User downloads DevSuite using Windows OS Given I am on DevSuite’s product download page And I am using Windows OS When I select the download button Then download the Windows OS version of DevSuite. h3. Scenario 11 Scenario: User navigates to DevSuite’s product downloads page using Linux OS Given I am on DevSuite’s product download page Then display “Install DevSuite” instead of “Download” in the CTA And underneath the button, display “for RHEL” after the version. h3. Scenario 12 Scenario: User downloads DevSuite using Linux OS Given I am on DevSuite’s product download page And I am using Linux OS When I select the “Install DevSuite” button Then bring me to DevSuite’s Hello World! Page. h3. Feature II: Site Downloads Page h3. Scenario 1 Scenario: User navigates to the site’s downloads page using Mac OS Given I am on RHDP downloads page Then underneath the download buttons in “Most Popular”, display “Version: xxx for Mac" And display “for Mac” underneath "Version: xxx" in “All Downloads”. h3. Scenario 2 Scenario: User navigates to the site’s downloads page using Windows OS Given I am on RHDP downloads page Then underneath the download buttons in “Most Popular”, display “Version: xxx for Windows” And display “for Windows” underneath "Version: xxx" in “All Downloads”. h3. Scenario 3 Scenario: User navigates to the site’s downloads page using Linux OS Given I am on RHDP downloads page Then underneath the download buttons in “Most Popular”, display “Version: xxx for Linux” But display "Version: xxx for RHEL" for DevSuite And display “for Linux” underneath "Version: xxx" in “All Downloads” But display "for RHEL" underneath "Version: xxx" for DevSuite And display “Install Devsuite” instead of “Download” in “Most Popular” and “All Downloads” sections And display “Install CDK” instead of “Download” in “All Downloads” section. h3. Scenario 4 Scenario: User downloads CDK using Mac OS Given I am on the site’s downloads page And I am using Mac OS When I select the download button Then download the Mac OS version of CDK (Filename ends in .dmg or contains “mac, “osx”, or “darwin”). h3. Scenario 5 Scenario: User downloads CDK using Windows OS Given I am on the site’s downloads page And I am using Windows OS When I select the download button Then download the Windows OS version of CDK (Filename ends in .exe). h3. Scenario 6 Scenario: User downloads CDK using Linux OS Given I am on the site’s downloads page And I am using Linux OS When I select the “Install CDK” button Then bring me to CDK’s Hello World! Page. h3. Scenario 7 Scenario: User downloads DevSuite using Mac OS Given I am on the site’s downloads page And I am using Mac OS When I select the download button Then download the Mac OS version of DevSuite. h3. Scenario 8 Scenario: User downloads DevSuite using Windows OS Given I am on the site’s downloads page And I am using Windows OS When I select the download button Then download the Windows OS version of DevSuite. h3. Scenario 9 Scenario: User downloads DevSuite using Linux OS Given I am on the site’s downloads page And I am using Linux OS When I select the “Install DevSuite” button Then bring me to DevSuite’s Hello World! Page. h2. Tasks h2. Review Process | Usability improvements for OS-specific product downloads | 2017-09-18 10:32 | 1
732594 | 12711990 | Story | h2. Requirements As a visitor, I want to: * click a 'Try It Now' button, which connects me to an online IDE with a Red Hat product running a quickstart. Note, this is work that we are contracting Codenvy to do with Che h2. Stakeholders Requirements: [~hwindzio] UX: [~tnolan@redhat.com] VD: Tiffany consulted with [~jbrock@redhat.com] Engineering: [~dcoughlin1] h2. Acceptance Criteria * Try it now feature appears on EAP product download page under the product header section. * Clicking "Launch EAP Now" h2. Review Steps * Banner appears under product hero * Links go to desired location * Reviewer is happy with results | Create 'Try it now' feature for EAP Kitchensink quickstart | 2017-09-15 12:58 | 744
732595 | 12711890 | Story | Given we have switched to a new vendor all the old marketing pixels that are firing in DTM needs to be disabled and removed from DTM. | Disable old Caffelli tags in DTM | 2017-09-15 04:09
732596 | 12711834 | Story | Following Disqus installation & activation, we need to be sure that Disqus comments, once approved for public display, are reaching the author. | Blog - Ensure Disqus comment notifications are reaching post authors | 2017-09-14 15:04
732597 | 12711789 | Story | Because Yoast SEO is now active, the blog no longer needs to have a custom canonical link supplied so: * Remove custom canonical link function from functions.php * Ensure the Yoast-supplied canonical links correctly match the required format for canonical link meta. | Blog - Remove custom canonical link | 2017-09-14 11:43
732598 | 12711787 | Story | Since Yoast has been activated, it's been pointed out that the posts' titles in the admin panel's posts page is pressed into a very thin column, making it difficult to read. Some CSS change and/or, perhaps, column removal should be applied to stretch this column back out to a more easily-read width. | Blog - Adjust column widths to make titles more legible in admin Posts page | 2017-09-14 11:42
732599 | 12711743 | Story | h2. Requirements In order to reliably test the RHD website download flow on pull-requests, we need to switch the staging download manager to the production version. h2. Design * No new design needed h2. Stakeholders * Engineering-only h2. Tasks: * Switch PR environment config to for download manager to production. * Agree on a solution to testing with [~dhladky@redhat.com] that will not interfere with production stats (for example we may use certain hardcoded users, or users with a particular email alias that will be omitted from stats) . * Enable download tests for PR test runs. h2. Review Steps * Pull-request environment uses production Download Manager. * Download tests are enabled on PR's. | Use production Download Manager in pull-request environment | 2017-09-14 08:57
732600 | 12711453 | Story | h2. Requirements In order to quickly allow outage messaging to be placed on the page in the most performant way we should utilize an alert component that will minimize the amount of HTML needed by Adobe Target experiences h2. Design * See https://redhat-developer.github.io/rhdp-frontend/patterns/content/notifications/#error h2. Stakeholders * Eng-only h2. Acceptance Criteria * A component exists called rhdp-alert * The component has a type (info, success, warning, error), size (xl), icon, heading, and text attributes that when changed update the layout and look of the component h2. Review Steps * Run the following script in the Dev Tools * {code:javascript} a = document.createElement('rhdp-alert'); a.type = 'error'; document.body.appendChild(a); {code} * There should be an error alert on the page | Create Alert Component | 2017-09-12 15:18 | 745
732601 | 12711451 | Story | h2. Requirements To eliminate the need for a complete server build in order to push important site or page-specific notifications to our users there should be placeholder elements, appropriately styled, available on relevant pages for Adobe Target to place messaging into. Details can be found in this document: https://docs.google.com/document/d/1rn61zVnsXFc_C5F4kdr8VMRi_scpTWUatGIZPgWdc70/edit# h2. Design * See https://redhat-developer.github.io/rhdp-frontend/patterns/content/notifications/#error h2. Stakeholders * UX - [~tnolan@redhat.com] * Eng - [~ldary] h2. Acceptance Criteria * As an Adobe Target user, I should be able to place site outage messages * Messages should be able to target an element with the class corresponding to one of three options: * * Download Manager (class: outage-download) * * Search (class: outage-search) * * Keycloak (class: outage-auth) h2. Review Steps * Using Target, set up three different experiences * Set the experience to update elements with those classes * Insert an rhdp-alert element with type="error" on the above elements * View the corresponding pages listed in the requirements doc | Create Messaging Placeholders | 2017-09-12 15:11 | 745
732604 | 12711190 | Story |  | Create new product page for Rust | 2017-09-11 10:12
732605 | 12711188 | Story |  | create new product pages for LLVM | 2017-09-11 10:12
732606 | 12711186 | Story |  | Create new product pages for Golang | 2017-09-11 10:11
732607 | 12711184 | Story | h2. Requirements Replace (in the same position/order) the "RUNTIMES" section with a "Languages and Compilers" section on /downloads and /products and mega-menu. Under the "Languages and Compilers" section add the following technologies (in the following order): # .NET Core # Clang/LLVM, Go, Rust # Red Hat Developer Toolset # OpenJDK On /products you will see that "Software Collections" is under the "RUNTIMES" category. This should be moved to the the "INFRASTRUCTURE" category. h2. Deliverable Dates # Pull Request build: 20th October # Live: 24th of October, and after the new technologies have their "Product" pages published. h2. Stakeholders * [~bodavis@redhat.com] * [~mguerett] | redo Technology section for October launch | 2017-09-11 10:10
732608 | 12711024 | Story | There is currently a cron job that runs in the blog, nightly, which imports the header and footer from the main RH developers site and and copies it into the Blog's Wordpress theme. Within the script there are a couple of string replacement filters which change the relative URL paths in the included HTML to absolute URL paths. Sometimes, the script applies this filter incorrectly. I think a previous copy of the script is still somewhere in OpenShift and that's what's being run. I'm going to try removing all copies of the script and re-applying the correct version. | Blog - Fix import script duplication from main RH Developers Site | 2017-09-10 14:50
732611 | 12710681 | Story |  | Review and update emails generated by KeyCloak | 2017-09-07 11:56 | 1
732612 | 12710515 | Story | Following discussions with Jairus Mitchell, there is a plan to implement Yoast SEO to the blog to some meta display issues and provide better meta discreptions, titles and search terms to individual posts and pages. The plugin is already being tested in the Blog stage right now. There are a few tasks that will need to be completed for implementation: * Ensure that the Open Graph tags rendered by Yoast are the correct format, or prevent them from being created altogether. Along with this, the curren Open Graph tags should be removed. * Make sure that page titles follow the correct format. * Make sure that the default settings are not available to be changed by non-admins. | Blog - Implement Yoast SEO | 2017-09-06 17:26
732613 | 12710457 | Story | Review and revise all the alert messages that users see, which are generated from the KeyCloak system during registration, log in and profile updates. This includes the wording and the style of the alert (error, warning, etc.) | Revise alert messages on KeyCloak pages | 2017-09-06 11:01 | 680
732616 | 12710421 | Story | Three new projects were added in ORG-3705 : .NET Core, Kompose and Minishift. An icon needs to be created and added for them. | Three Projects Need Icons in developers.redhat.com/projects | 2017-09-06 09:06
732618 | 12710262 | Story | We need to add additional products to the /stack-overflow dropdown. starting Sept 5th (Wednesday), we will make all of the developer product forums read-only. We discovered that not all product stackoverflow tags are represented in the dropdown, and are pulling in the corresponding tags. These need to be added: Red Hat JBoss Data Grid - (maps to tag: redhat-datagrid) Red Hat JBoss AMQ - (maps to tag: amq) Red Hat JBoss BRMS - (maps to tag: redhat-brms) Red Hat JBoss BPM Suite - (maps to tag: redhat-bpm) Red Hat JBoss Data Virtualization - (maps to tag: redhat-datavirt) .NET Core for Red Hat Enterprise Linux - (maps to tag: rhel.net) | Need to add additional products to the /stack-overflow dropdown | 2017-09-05 15:59
732620 | 12710236 | Epic | This is an epic to hold the Q3FY18 work that's not scheduled in the PDD and not within another epic's scope of work. | Visual Design work outside of PDD (Q3FY18) | 2017-09-05 12:22 | 750
732622 | 12710218 | Story | h2. Requirements We need to remove multiversion from our install. This is causing a myriad of issues for us. h2. Design N/A h2. Stakeholders Engineering: [~jporter@redhat.com] h2. Acceptance Criteria There is no more multiversion module installed on the site, or listed in the extensions within Drupal h2. Review Steps Check the extensions and verify there is no "multiversion" in the list. | Spike: Remove multiversion | 2017-09-05 11:17 | 712
732623 | 12710217 | Story | Forums should become read-only on 9/6 (wednesday). Before that happens, we need to change the text directly under the forums on this page https://developers.redhat.com/forums/ to read: “PLEASE NOTE: This <product forum> is now read only. You can find questions about this product on our Stack Overflow page, or you can post your questions to StackOverflow using relevant tags. Read more on why we doing this ” Also, the forum name should no longer have the link to the forum landing page. We need to un-embed that link. | replace text underneath the forum titles | 2017-09-05 11:17
732624 | 12710173 | Story | This books listing (https://developers.redhat.com/resources/#!type=book) is missing a book. Missing book is: https://developers.redhat.com/promotions/microservices-for-java-developers/ | Books Page missing a Book | 2017-09-05 08:35
732625 | 12710127 | Epic | h2. Overview This is a standard 'grouping' Epic added every quarter. It groups together a set of improvements to the /search page that are planned for completion within the quarter. h2. Team UX: Done on a per-story basis. VD: Done on a per-story basis. Eng: [~ldary24] h2. Additional Information As this is a 'grouping' epic, further information (such as wireframes and VD mockups) is added to individual stories, where needed. | Search Page Improvements (Q3FY18) | 2017-09-05 05:35 | 739
732638 | 12709672 | Story | h2. Requirements Currently in Drupal it appears it is only possible to place custom text on the product download page after the ALL DOWNLOADS section where it is easily missed. Ideally there should be the ability to place text before either the ALL DOWNLOADS section or the TRY IT section. Cc: [~mguerett] Allow freeform text to be added to the downloads paragraph. It will display above the "Try It" section. h2. Design * [~tnolan] / [~gdoyle-1] h2. Stakeholders * [~tnolan] * [~mguerett] h2. Acceptance Criteria * New formatted text area in the Downloads paragraph labelled "Important Information" -limited to 500 characters- * New area on the template with "Important Information" as the header, only displayed if there is content in the new field * Current "Main" is relabelled to "Additional Information" * Additional help text added to both fields (see comments section) h2. Review Steps * Add content to the new field, verify it displays on the downloads page * Verify if there is no entry in the field there is also no header displayed | Ability to place custom text above the download links on product download page. | 2017-08-31 16:15
732643 | 12709631 | Story | h2. Requirements The Feedback box currently has a 'Yes', 'No' and comment section. Requirements dictate that an email will be sent to the concerned product managers so that they are aware of feedback received from registrants. 1. Where will the comments be stored? They are going to be private; however, we don't have a place to hold those comments. 2. How will we send the data via email to the correct product managers? h2. Design * None h2. Stakeholders * UX - [~gdoyle-1] * Eng - [~dcoughlin1] * VD - None * Review - TBD h2. Acceptance Criteria * A process/technology has been decided for sending feedback comments to product teams. h2. Review Steps N/A | SPIKE - Investigate where and how emails will be sent from the Feedback Box | 2017-08-31 11:17 | 729
732644 | 12709404 | Story | Create a chart showing jboss.org download summary over the last 12 months displaying the top 6 downloaded projects (unversioned) | Project download summary | 2017-08-30 08:37
732646 | 12709270 | Story | Currently the 404 page for the site is not exported from Drupal. It instead lives as a static resource that is copied as part of the export process. This means that the page can quickly get out of date and even break if it is referencing incorrect resources as seen in DEVELOPER-4387. h2. Background The reason why the 404 page is currently a static resource is due to the project upgrading to Drupal 8.3.1. As part of the 8.2.0 release, changes were made to the way in which Drupal handled caching of 404 responses. This change is obviously part of the 8.3.1 release. Whatever changed as part of this work meant that the 404 page in Drupal started to return a HTTP 404 status code rather than a HTTP 200 status code when accessed by the export process. This causes the export process to believe (incorrectly) that the page does not exist in Drupal and hence it fails the export with a missing page. To work around the above, the 404 page was excluded from the sitemap.xml of Drupal. This in-turn meant that the page was no longer included in the export process and had to be turned into a static resource that is copied into the correct location of the export directory once the process has completed. The current 404 page can be [found here in the GitHub repo¦https://github.com/redhat-developer/developers.redhat.com/blob/master/_docker/lib/export/static/404-error/index.html] for the project. h2. Stakeholders * [~ldary] * [~lightguard] h2. Acceptance Criteria {code} Given that I want to make changes to the 404 page of the site And I make these changes in Drupal And the export process is run after I have made my changes Then the new version of the 404 page will appear on the site {code} h2. Review Steps Make a change to the 404 page of the site and then re-run the export. Your changes should show up as the new 404 page. | SPIKE: Investigate solutions for the 404 page not being exported from Drupal | 2017-08-29 10:40 | 1
732647 | 12709222 | Story | As noted by [~mguerett], right now when a search query is performed, it presents results in a list in both the main site and the columns in admin panels (Example¦https://developers.redhat.com/blog/?s=ebook]), but only in the default order of relevance. A couple of filtering parameters will be added to the results page: * Alphabetical Title Order (reversible, too) * Publishing date (also reversible) | Blog – Add order sorting for general search results | 2017-08-29 09:58
732650 | 12708650 | Story | The front-end unit tests randomly fail, even when there are no changes related to the JS code of the site. This causes developers to spend time investigating build failures that are no related to their code. See the attached screenshot for failures that occurred when I had not made any changes to the JS. h2. Stakeholders: - [~ldary24] h2. Acceptance Criteria: {code} Given that I have not made any changes to the JS code of the site And all JS Unit tests are currently passing And I run the JS Unit test suite Then no JS unit tests should fail {code} h2. Review steps - Ensure that the JS unit tests can be run multiple times without any failure | Front-end JS Unit tests are flaky | 2017-08-24 06:11
732651 | 12708198 | Story | HI Axel and Dan, Attached please find a new tag for our site. This tag will work for all our media programs. So we will no longer have a tag JUST for FB and then another for everything else. I've cc'd Maria Mohammad on this email. She's the contact at Liquid Advertising that can help if you run into any technical issues. Once implemented - if there's a way you can work with Maria to test this to make sure it's tracking correctly that would be great. I meant to also say that we need this live for Sept 1st. Thank you! | New tag for Media Programs | 2017-08-21 13:45
732652 | 12708182 | Story | h2. Requirements Figure out where all of our feedback data will end up going. Get in contact with Marcia (adobe analytics) to see if we can store feedback analytics there. h2. Design * None h2. Stakeholders * UX - [None] * Eng - [~dcoughlin1]] * VD - [None] * Review - [None] h2. Acceptance Criteria * Storage for feedback metrics has been decided. h2. Review Steps * None | Spike - Investigate where data collected from "Feedback on Content" will live | 2017-08-21 10:58 | 729
732653 | 12708109 | Story | ¦¦¦Action Item¦¦¦¦Reporter¦¦Source¦¦Description¦¦Status¦ ¦ None ¦ ¦ ¦The Metrics that were reported in the presentation is now fully automated in Klipfolio, thus we'll stop manually creating decks for reporting purposes.¦ ¦ | RHD Weekly Dashboard - 25 August 2017 | 2017-08-21 04:17
732654 | 12708108 | Story | ¦¦¦Action Item¦¦¦¦Reporter¦¦Source¦¦Description¦¦Status¦ ¦ 1¦Heinz Windzio ¦Email ¦Add Monthly Engaged Members Chart¦Done ¦ | RHD Weekly Dashboard - 18 August 2017 | 2017-08-21 04:17
732655 | 12708069 | Story | For here, http://developer-drupal.web.prod.ext.phx2.redhat.com/products/dotnet/overview, it's not displaying the at the specified time. I want it to be this: https://youtu.be/sIEE-_NK_Wo?t=42 | Need to display Product Overview videos at a specified time | 2017-08-18 16:41 | 666
732656 | 12708060 | Story | An exploration dive into why versions are not working with Drupal. Relates to DEVELOPER-4359. I really don't know what I'm expecting to find or come out of this, but it needs to be investigated as part of the "stability of Drupal" concerns people have been having. h2. Design * NA h2. Stakeholders * Engineering: [~jporter@redhat.com] h2. Acceptance Criteria * A cause is determined, and hopefully it's something we can fix h2. Review Steps * N/A | SPIKE: Explore why Drupal revisions are not working | 2017-08-18 12:12 | 712
732658 | 12708054 | Epic | Improvements to RHDP KeyCloak pages and other changes in support of the larger Red Hat SSO project. h2. Requirements TBD - Currently within individual stories/issues already assigned to this Epic. h2.Team Engineering: [~velias@redhat.com], [~lkrzyzan] Front-end Dev: [~aarreola@redhat.com] UX: [~tnolan] | Improve user identity and access management experiences (G Train) | 2017-08-18 11:45 | 728
732661 | 12708048 | Story | Cheatsheets will need to be included in this. Further details needed | Create Web Component for Standardizing Time | 2017-08-18 11:29 | 1
732662 | 12707923 | Story | Please add indent and outdent options for large text/body fields | Add "indent" and "outdent" buttons to drupal editor | 2017-08-17 15:26 | 1
732663 | 12707768 | Epic | h2. Requirements All broken links must be fixed on the RHDP website. There might need to be some exceptions, as many pages are generated from source content that may have broken links. E.g the quickstarts. Exceptions need to be approved by [~erooney8] and [~hwindzio@redhat.com]. h2. Stakeholders PM: [~hwindzio@redhat.com] h2. Tasks By Friday the 18th of August: # See the spreadsheet of broken links [here¦https://docs.google.com/spreadsheets/d/1JD0X_12JI3uikscSd6hKDiZYyyzjFekzbVbqjUcxCNU/edit?userstoinvite=jparenti@redhat.com&ts=59959e2d#gid=0] # Mark each issue as in either content (can be fixed by content editor in Drupal) or layout (needs fixing in code) # [~paul.robinson@redhat.com] to email Erin on Friday with the list of content changes # [~paul.robinson@redhat.com] to email Erin and the team, to discuss the escalation process, in my absence if there's a lack of response from someone on her team. h2. Review steps # Ensure the Blinkr report only contains references to broken links on the approved exceptions list. | Fix all Broken Links on the RHDP site | 2017-08-16 11:39 | 738
732664 | 12707759 | Story | Include the PatternFly icon set in the website styles so we can use these on our page: http://www.patternfly.org/styles/icons/ | Add PatternFly icon (font) library to website | 2017-08-16 10:52 | 41
732667 | 12707661 | Story | Currently I am set as the owner of all Jenkins nodes and all jobs within Jenkins. This needs to be updated to reflect that Lukas/Libor are now the owners of the RHDP Jenkins instance. h2. Stakeholders * [~lkoranda@redhat.com] * [~lkrzyzan] h2. Review steps Ensure that the owner of all jobs and all nodes within Jenkins are listed as Libor/Lukas | Update all Jenkins ownership and notifications to Lukas & Libor | 2017-08-16 04:38 | 674
732668 | 12707660 | Story | As part of the hand-over, ensure that Lukas and Libor have access to all of the RHDP infrastructure. This includes: * Production VM * Staging VM * Jenkins * GitHub Git Repositories * Stumpjumper * Jenkins Slaves VM * DockerHub h2. Stakeholders: * [~lkoranda@redhat.com] * [~lkrzyzan] h2. Review steps Verify with Lukas and Libor that they can access all the required systems. | Verify access to all RHDP infrastructure for Lukas & Libor | 2017-08-16 04:36 | 674
732670 | 12707611 | Story | h2. Requirements SEO will benefit from not putting permanently visually hidden items onto the page. Specifically, this was targeting field labels that are set to have a class of 'visually_hidden' or 'visually-hidden'. They will never be shown, so they should not be put into the document. h2. Design * NA (no visual changes) h2. Stakeholders * Engineering-only h2. Acceptance Criteria * Topic and Product pages, specifically, do not have any elements with a class of "visually_hidden" or "visually-hidden" h2. Review Steps * Visit the following pages and run the below script in the dev console to ensure there are no elements * /products/datagrid/overview/ * /topics/containers/ * /promotions/building-reactive-microservices-in-java/ * /summit-is-for-developers/ * {code:javascript}document.querySelectorAll('.visually_hidden, .visually-hidden').length{code} | Remove visually hidden items from templates | 2017-08-15 14:53 | 6
732671 | 12707603 | Story | h2. Requirements Specifically Topic pages, but could stand to look across the site at how page structure places secondary content before primary content simply to accommodate the style of the page layout. Example is the gray box on the right-hand side of topics page is actually before the other content in the document. h2. Design * NA (no visual changes should take place though) h2. Stakeholders * Engineering-only h2. Acceptance Criteria * Document structure matches priority on topics pages * Any additional changes to priority are also done. h2. Review Steps * Visit topic pages to see the page structure and ensure that the secondary content is after the primary content in the page. | Adjust document to place secondary content after primary | 2017-08-15 14:04 | 698
732672 | 12707602 | Story | h2. Requirements As mentioned in this document ( https://docs.google.com/document/d/1Y9fxGjhuwf1v9KAg-1Jb_euFeSMQjgFsENio6Tl1woU/edit?ts=59931d86 ) our current page structure uses the H1 tag for the logo, and the rest of the page structure is not properly using the hierarchy outlined here: https://www.w3.org/TR/2014/REC-html5-20141028/sections.html#headings-and-sections h2. Design * NA (no visual differences should happen due to this story) h2. Stakeholders * Approval - [~hwindzio] * UX - [~tnolan@redhat.com] * VD - [~jcobb@redhat.com] * QA - [~ihamilto@redhat.com] * Eng - [~ldary] h2. Acceptance Criteria * All pages follow a more standard approach for usage of h1-h6 tags * Heading tags are nested without skipping order * Heading tags reset for section or article differences h2. Review Steps * Check all pages for proper page hierarchy using h* tags | Correct Page Heading Hierarchy | 2017-08-15 13:58 | 698
732673 | 12707562 | Story | I'm making this item its own JIRA project. It was part the larger Home page improvement discussion... Per a suggestion by [~jessk_jira] an email signup form is being added to the sidebar of the blog. Since it wasn't clear whether there was some type of RH marketing component available, a standalone plugin has been found, installed in staging and tested out. Once some CSS that will reformat its appearance has been cached into production, the signup form can be made live. | Add Quick Email Signup Form to blog | 2017-08-15 10:43
732674 | 12707557 | Story | In many post pages on the blog, an Open Graph tag is appearing that uses the default OpenShift URL instead of the correct https://developers.redhat.com/blog/ for the URL root. An example is here: <meta property="og:url" content="https://devblog-redhatdevelopers.rhcloud.com/2017/06/07/new-level-of-automation-with-ansible/" /> The Jetpack/Open Graph settings need to be updated to display the correct tag. | Change Jetpack/Open Graph default URL to match correct blog address | 2017-08-15 10:04 | 201
732675 | 12707547 | Story | Utilize the selection-sharer plugin: https://wordpress.org/plugins/selection-sharer/ Should allow the blog content to be shared when highlighted. Based on the code here: https://github.com/xdamman/selection-sharer | Selection Sharer Wordpress Plugin | 2017-08-15 09:17 | 770
732679 | 12707430 | Story | Date to go live: TBD [~jessk_jira] Mockup: http://design.jboss.org/redhatdeveloper/marketing/git_cheatsheet/hero/images/RHDP_heromockup_gitcheatsheet_r1v1.png Content: headline: Git Cheat Sheet subhead: Git command sequence, CLI, branches and more. CTA: Download Now Target URL: TBD [~jessk_jira] Images for production. Mobile: http://static.jboss.org/images/rhd/hero/RHDev_homehero_mobile_gitcheatsheet_14aug2017.jpg Tablet: http://static.jboss.org/images/rhd/hero/RHDev_homehero_tablet_gitcheatsheet_14aug2017.jpg Desktop: http://static.jboss.org/images/rhd/hero/RHDev_homehero_desktop_gitcheatsheet_14aug2017.jpg Note: The background image is designed NOT to repeat. it’s a fixed size so please have it fill the available space. [~paul.robinson] [~aarreola@redhat.com][~jessk_jira] | Implement Hero for "Git Cheat Sheet" | 2017-08-14 15:31
732680 | 12707415 | Story | Mockup: http://design.jboss.org/redhatdeveloper/marketing/dotnet_cheatsheet/hero/images/RHDP_heromockup_dotnet_r1v1.png Images for production. Mobile: http://static.jboss.org/images/rhd/hero/RHDev_homehero_mobile_dotnetcore_14aug2017.jpg Tablet: http://static.jboss.org/images/rhd/hero/RHDev_homehero_tablet_dotnetcore_14aug2017.jpg Desktop: http://static.jboss.org/images/rhd/hero/RHDev_homehero_desktop_dotnetcore_14aug2017.jpg headline: .NET Core on Red Hat Enterprise Linux Cheat Sheet subhead: Getting started, running a program in a Linux container and create an image. CTA: Download now Target URL: forthcoming (see @jessk) //note: CTA is white filled rectangle with #FF0000 text. The background image is centered. [~jessk_jira] [~paul.robinson@redhat.com] Work with Jessica to determine the go live date for the Hero. | Implement Hero for ".Net Core Cheat Sheet" | 2017-08-14 12:27
732682 | 12707389 | Story | h2. Requirements Create a page for www.jboss.org that allows the user to decide if they want to go to the RHDP site, or the JBoss Community site. The page is pretty simple, and can be created in just HTML. It should be hosted on file-management in the location at which the current JBD website is exported to. It is not expected that this will need to change much or even ever. Please test this on http://www.stage.jboss.org/ first to make sure the page renders correctly. h2. Stakeholders * [~nmcl2001] * [~hwindzio] h2. Design [~jbrock@redhat.com] to provide VD. Due (ideally) by CoB weds, if not CoB Thurs. h2. Acceptance Criteria & Testing Non required. h2. Review Process * Check the links on the page go to the correct locations * Check the stakeholders (mentioned above) are happy with the page. | Create www.jboss.org redirect options page | 2017-08-14 10:57
732683 | 12707180 | Story | For improved SEO, we are advised to use higher level headers and, for example, move H3 to H2, H2 to H1, etc. The problem is that the current styling has H1 and H2 to be huge. Can we adjust this formatting so we can use H1 and H2 as common headers and improve our SEO? cc: [~jessk_jira] [~tnolan@redhat.com] [~jcobb@redhat.com] [~paul.robinson@redhat.com] | Need to change drupal header styling for better SEO | 2017-08-11 14:08
732684 | 12707137 | Story | Please remove the RHEL part and make it ".NET Core" only | Change .NET Core title on Technology pull-down | 2017-08-11 09:22
732685 | 12706946 | Story | ¦¦¦Action Item¦¦¦¦Reporter¦¦Source¦¦Description¦¦Status¦ ¦ None ¦ ¦ ¦No feedback for additional changes received for this week¦ ¦ | RHD Weekly Dashboard - 11 August 2017 | 2017-08-10 08:38
732686 | 12706477 | Story | We need a link in the footer, maybe called "Newsletter signup". I suggest it go to the right of 'contact us'. This link should bring you to a form, that tells you what the newsletter provides, the frequency in which it's sent, and any other salient details. [~jessk_jira] Can you create the text for that page and send it to me? It should also be a form, that asks you for your email address submission. | Create a link in the footer that brings you to a newsletter sign up | 2017-08-07 17:30
732687 | 12706460 | Story | Red Hat Application Migration Tool needs to be added as a dropdown on the stackoverflow dropdown menu. https://developers.redhat.com/stack-overflow/#!q= | Add RHAMT to Stack Overflow Dropdown | 2017-08-07 13:57
732688 | 12706057 | Story | ¦¦¦Action Item¦¦¦¦Reporter¦¦Source¦¦Description¦¦Status¦ ¦ None ¦ ¦ ¦No feedback for additional changes received for this week¦ ¦ | RHD Weekly Dashboard - 4 August 2017 | 2017-08-03 12:19
732689 | 12705905 | Story | Full Drupal going down at 0700 UTC (0000 Pacific/0300 AM Eastern/0800 UK) every night. Needs to be broadcast to the group. Jenkins jobs will need to be updated as well. | Only rebuild Drupal server once per day | 2017-08-02 16:49 | 712
732692 | 12705847 | Story | h2. Requirements All of the product forums listed in /forums/ should have the following message under the product name: “PLEASE NOTE: This forum will become read-only on September 1st, 2017. You can now post your Red Hat <product> developer questions to StackOverflow using the <relevant tag>. Why are we doing this? <link to artcile>.” Article: https://developers.redhat.com/forumstostackoverflow/ h2. Stakeholders PM: [~hwindzio@redhat.com] h2. Steps to review 1. go to /forums/ 2. Check that all of the products have the messaging above along with the related tags link and link to the article | Forums - Add read-only notice to all products | 2017-08-02 09:34
732693 | 12705838 | Story | h2. Requirements Create the middleware landing page users will see once they click on _'Learn More About Middleware'_ on jboss.org. If the user comes directly from jboss.org, the _'Welcome jboss.org members!'_ alert should be displayed. URL will be: /middleware h2. UX & VD Work InVision Project: https://redhat.invisionapp.com/share/XHC8PHGCJ#/244799983_Middleware_-_Desktop_HD Visual Design: TBD h2. Stakeholders * UX: [~tnolan] * VD: [~jbrock@redhat.com] * PM: [~hwindzio] h2. Acceptance Criteria h4. SCENARIO 1: User is referred to the /middleware page from jboss.org Given I am entering the /middleware page When I am referred by the Learn More About Middleware CTA on jboss.org Then show the Welcome JBoss members info alert at the top of the /middleware page And move down the page title and description content in the page header so it's all vertically aligned within the page header section h4. SCENARIO 2: User is not referred to the /middleware page from jboss.org Given I am entering the /middleware page If I am NOT referred by the Learn More About Middleware CTA on jboss.org Then do NOT show the Welcome JBoss members info alert at the top of the /middleware page | Create /middleware Landing Page | 2017-08-02 09:12
732696 | 12705382 | Story | Adding this because first attemp to do so failed, causing a 503 error in the admin panel. Noting that this happened during the previous upgrade just a few weeks ago but then as now I'm not sure why. | Update minoOrange plugin from version 4.8.25 to 4.8.26 | 2017-07-30 13:39
732698 | 12704933 | Story | !https://redhat.invisionapp.com/static-signed/live-embed/68589359/244799983/7/latest/tFepq84dtisj8s8qhln4aCVgX309RWkWDJTlM7lEkc9lE6hlE9L5pomPWVGREUf1b598SrlEApPDAf8Zz8QgmnwQMAlE/Middleware---Desktop-HD-2x.png¦width=50%,height=auto! | testing live embed with JIRA | 2017-07-26 16:45
732700 | 12704708 | Story | [~jessk_jira] Images for production. Mobile: http://static.jboss.org/images/rhd/hero/RHDP_homehero_rhmapcheatsheet_mobile_background.png Tablet: http://static.jboss.org/images/rhd/hero/RHDP_homehero_rhmapcheatsheet_tablet_background.png Desktop: http://static.jboss.org/images/rhd/hero/RHDP_homehero_rhmapcheatsheet_desktop_background.png headline: Red Hat Mobile Application Platform Cheat Sheet subhead: Projects, services and APIs, drag and drop apps and more. CTA: Download now Target URL: forthcoming (see [~jbrock@redhat.com] or @jessk) //note: CTA is white filled rectangle with #3F9C35 text Mockup: http://design.jboss.org/redhatdeveloper/marketing/rhmap_cheatsheet/hero/images/RHDP_heromockup_rhmapcheatsheet_r1v1.png | Implement hero for "Red Hat Mobile Application Platform Cheat Sheet" | 2017-07-25 16:03
732705 | 12704433 | Story | Date to go live: TBD [~jessk_jira] Mockup: http://design.jboss.org/redhatdeveloper/marketing/openshift_cheatsheet/website/images/RHDP_hero_openshiftcheatsheet_r1v1.png Content: headline: Red Hat OpenShift Cheat Sheet subhead: A command list to help you manage an application’s lifecycle. CTA: Download Now Target URL: TBD [~jessk_jira] Images for production. Mobile: http://static.jboss.org/images/rhd/hero/RHDev_homehero_mobile_openshiftcheatsheet_24jul2017.png Tablet: http://static.jboss.org/images/rhd/hero/RHDev_homehero_tablet_openshiftcheatsheet_24jul2017.png Desktop: http://static.jboss.org/images/rhd/hero/RHDev_homehero_desktop_openshiftcheatsheet_24jul2017.png SVG of OpenShift logo: http://static.jboss.org/images/rhd/hero/openshiftlogo.svg Please note the preferred rendering of the desktop image is horizontal repeat, no stretch. [~paul.robinson] [~aarreola@redhat.com][~jessk_jira] | Implement Hero for "Openshift Cheat Sheet" | 2017-07-24 17:05
732707 | 12703448 | Story | Following the completion of DEVELOPER-4008 we now have the general configuration for RHDP infrastructure managed by Ansible. Our IT managed infrastructure in PHX2 is managed by Puppet and not Ansible. Therefore we need to replicate the Ansible configuration in Puppet 3 so that it can be integrated into the IT puppet management of our infrastructure. h3. Stakeholders * [~lkoranda@redhat.com] h3. Acceptance Criteria: {code} Given that I have checked out the Puppet configuration And I am running a Puppet development environment Then I can apply the replica Puppet configuration to the development environment {code} h3. Review steps * Checkout the Puppet configuration * Apply it to the local development environment | Build: Replicate Ansible configuration in Puppet 3 | 2017-07-24 10:47 | 674
732711 | 12703188 | Story | h2. Requirements Provide hooks for analytics tracking in Clicktale. Adobe tracking is already able to grab OneBox events. Goal of this story is to ensure that we have data and metrics in place in the code to support OneBox. Initial requirements and information: https://docs.google.com/document/d/175G8KBHeQNJ7ZE4L7cl0bOKu2rMJYZMdoOCb0xYOYu4/edit h2. Design * NA h2. Stakeholders * UX/Clicktale/Approval - [~tnolan] * Eng - [~ldary] h2. Acceptance Criteria * Links in OneBox content will append a querystring value to the URL for Clicktale to reference * Value will be in the form onebox={product} h2. Review Steps * Navigate to search page and query for a valid OneBox term (rhel, fuse, devsuite) * Note that all links contained in the OneBox have the added querystring parameter appropriate for their product | OneBox Search - Analytics & Metrics | 2017-07-21 15:44 | 773
732714 | 12702886 | Story | Review and provide design feedback and direction for the new blog author bio page. Example: https://developers.redhat.com/blog/author/rafabene/?displaynew=blog2017 | Visual Design for Blog Author Bio page | 2017-07-20 09:23 | 750
732715 | 12702876 | Story | ¦¦¦Action Item¦¦¦¦Reporter¦¦Source¦¦Description¦¦Status¦¦ ¦1¦Mark Newton¦Weekly Meeting¦Add OSO (Pro) registration numbers to 'Registrations be web assets' Klip¦Done ¦ ¦2¦Heinz Windzio¦Wednesday Meeting¦Segment all RHDP dashboard data with "Rogue IP" and "External Visitors" Adobe Segments¦Done ¦ ¦ 3¦Heinz Windzio ¦Klipfolio Comment ¦ "remove fuse service works and mobile from this list of products" I.E remove fuse service works and JBoss mobile from the download charts in RHDP dashboard ¦Done¦ | RHD Weekly Dashboard - 28 July 2017 | 2017-07-20 08:51
732716 | 12702860 | Story | Automated the Best performing assets in Klipfolio using the spreadsheet RHD Marketing Metrics and Tracking https://docs.google.com/a/redhat.com/spreadsheets/d/19CqpECdQWrmAyATK9ofkX84hEUan9vyvy33PPklnOyw/edit?usp=sharing in Klipfolio | Best Performing assets (for registrations) | 2017-07-20 07:27 | 775
732717 | 12702859 | Story | Automated the Paid Media Metrics in Klipfolio from the spreadsheet RHD Marketing Metrics and Tracking https://docs.google.com/a/redhat.com/spreadsheets/d/19CqpECdQWrmAyATK9ofkX84hEUan9vyvy33PPklnOyw/edit?usp=sharing in Klipfolio | Paid Media Metrics | 2017-07-20 07:26 | 775
732718 | 12702764 | Story | Date to go live: Monday 08/07 or Tuesday 08/08 Mockup: http://design.jboss.org/redhatdeveloper/marketing/eap7_cheatsheet/website/images/RHDP_hero_advancedEAP7cheatsheet_r1v1.png Content: headline: Advanced Red Hat JBoss Enterprise Application Platform 7 Cheat Sheet subhead: Get commands for socket bindings, logging, class loading, role-based access control and more. CTA: Download Now Target URL: https://developers.redhat.com/cheat-sheets/advanced-red-hat-jboss-enterprise-application-platform-7/ Images for production. Mobile: https://static.jboss.org/images/rhd/hero/RHDev_homehero_mobile_adveap7cheatsheet_19jul2017.png Tablet: https://static.jboss.org/images/rhd/hero/RHDev_homehero_tablet_adveap7cheatsheet_19jul2017.png Desktop: https://static.jboss.org/images/rhd/hero/RHDev_homehero_desktop_adveap7cheatsheet_19jul2017.png Please note the preferred rendering of the desktop image is designed to be centered on a blue (#0068ba). If this is not possible, please repeat horizontally and NOT stretch the image. [~paul.robinson@redhat.com] [~aarreola@redhat.com][~jessk_jira] | Implement Hero for "Advanced EAP Cheat Sheet" | 2017-07-19 16:20
732722 | 12702448 | Story | [~jessk_jira] Images for production. Mobile: https://static.jboss.org/images/rhd/hero/RHDev_homehero_mobile_introeap7cheatsheet_18jul2017.png Tablet: https://static.jboss.org/images/rhd/hero/RHDev_homehero_tablet_introeap7cheatsheet_18jul2017.png Desktop: https://static.jboss.org/images/rhd/hero/RHDev_homehero_desktop_introeap7cheatsheet_18jul2017.png Please note the preferred rendering of the desktop image is designed to be centered on a red (#cc0000). If this is not possible, please repeat horizontally and NOT stretch the image. headline: Command syntax, batch processing, and configuration file short-cuts. subhead: Introduction to Red Hat JBoss Enterprise Application Platform 7 Cheat Sheet. CTA: Download now Target URL: https://developers.redhat.com/cheat-sheets/intro-red-hat-jboss-enterprise-application-platform/ Mockup: http://design.jboss.org/redhatdeveloper/marketing/eap7_cheatsheet/website/images/RHDP_hero_introEAP7cheatsheet_r1v1.png | Implement Hero for "Intro to EAP 7 Cheat Sheet" | 2017-07-18 11:23
732725 | 12702276 | Story | As part of an SEO audit, we learned that blog pages should only have 1 Heading1 line on any given page. On some pages, this might be difficult to accomplish (any kind of category or archive page, including the front page, as examples) but moving forward, anyone logging into edit their post could have the option of an h1 tag either removed, or H1 could simply be the label on the actual H2 tags | Remove <h1> tags as an editing option from post editor | 2017-07-17 17:52
732726 | 12702270 | Story | In the Community tab of a Technology, there's an item to check that reads "Hide Get Started". I believe this should read "Hide Hello World tab". Mike h2. Design N/A h2. Stakeholders Business: [~mguerett] h2. Tasks * Update the labels mentioned h2. Acceptance Criteria * Label matches proposed text | update text to match "Hello World" tab | 2017-07-17 16:18 | 712
732727 | 12702237 | Story | ¦¦¦Action Item¦¦¦¦Reporter¦¦Source¦¦Description¦¦Status¦¦ ¦1¦¦Mark Newton¦Analytics 1-to-1 ¦Take snapshot for detailed registrations metrics rather than copy/past the data in slide 5¦Done¦ | RHD Weekly Dashboard - 21 July 2017 | 2017-07-17 11:40
732729 | 12702193 | Story | In order to be able to run and provide more comprehensive reports on Cheat Sheets, we should set the content type in adobe analytics. These values are currently empty and thus not able to be used for content-related reports. * Content Type (v7) (evar7) = Cheat Sheet * prop9 = Cheat Sheet | Reporting: Set Adobe Analytics variables for Cheat Sheets | 2017-07-17 09:10 | 742
732730 | 12702001 | Story | For pull requests we make use of the GitHub Pull Request Builder plugin. This plugin sets up a number of build job parameters that are then passed to downstream jobs to determine which branch should be checked out of Git when running a build. This approach is fine, but the parameter names used by downstream jobs are not consistent meaning that it quickly becomes confusing trying to track job parameters through the full build flow. Additionally any build related code that relies on the value of these variables should be updated to look for the consistent versions. h3. Stakeholders * RHDP dev team h3. Acceptance Criteria {code} Given that a build job has been triggered by the Git Hub Pull Request And I can see the list of downstream jobs for that job And I can see the list of parameters passed to those jobs Then I can see that the names of the parameters passed between jobs are consistently named {code} h3. Review steps: * Starting at the Pull_Request_Build job in Jenkins, ensure that parameter names are consistent for all downstream jobs and that you can easily follow what is being passed around | Build: Make parameter naming/passing between Jenkins jobs consistent | 2017-07-14 06:08
732731 | 12701867 | Story | I want to be able to add this video to the .NET technology Overview page: https://goo.gl/4xDfGr Drupal currently rejects it as an invalid video. | Support additional video format: https://goo.gl/ | 2017-07-13 14:02 | 666
732732 | 12701681 | Story | We need to add a file to the RHDP server so that we can support cross-domain paths with OSIO. The OSIO team will also be adding a file to their system to support this. Many details of this are in an email thread which is way too big to post here. I'm not sure what's all in this, but here is also a meeting recording where this change was discussed with RH Marketing Ops: https://zoom.us/recording/play/djsjnXC5U4XrdoHch1l5LB9pXA60FidUqWNTGSfye2iuc8KaxM231ma25cNzaABQ. Per Uri (Clicktale Developer that is helping us figure this out): {quote}As per the call we had today, please save the attached file and rename it to .htm and then place it on both physical servers in a defined folder location such as: https://openshift.io/clicktale/ctIframe.htm https://developers.redhat.com/clicktale/ctIframe.htm These files need to be in HTTPS only. I will then create the code that will inject the iframes which will point to the above URLs. Thanks Uri{quote} | Add Clicktale file to support cross-domain support with OSIO | 2017-07-12 11:31
732733 | 12701671 | Story | h2. Requirements The new OneBox component should be styled to match visual design work h2. Design * TBD - [~jcobb@redhat.com]] h2. Stakeholders * VD: [~jbrock@redhat.com] * Approval: [~hwindzio] h2. Acceptance Criteria * OneBox visual appearance matches visual design h2. Review Steps * Navigate to the search page * Search for multiple OneBox-matching entries * Verify visual appearance | OneBox - OneBox Styling | 2017-07-12 10:51 | 773
732734 | 12701670 | Story | h2. Requirements End-to-end testing should be done to verify that the OneBox fulfills all scenarios. h2. Design * NA h2. Stakeholders * QA: [~ihamilto@redhat.com] h2. Acceptance Criteria {code} Feature: OneBox for On-Site Search Scenario: User searches for a string that is associated with a Product OneBox Given I am using on-site search When I submit the search And the search term matches <string> Then show the OneBox for <product> And display it at the top of the search results And show the <product> information in the box And display only the links that have corresponding pages on the website Scenario: User selects the Title of the product on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> Title Then bring me to the <product’s> Overview page Scenario: User selects the View Downloads button on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> View Downloads button Then bring me to the <product’s> Download page Scenario: User selects the Hello World! molecule (icon and/or text) on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> Hello World! molecule Then bring me to the <product’s> Hello World! page Scenario: User selects the Docs and APIs molecule (icon and/or text) on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> Docs and APIs molecule Then bring me to the <product’s> Docs and APIs page Scenario: User selects the Help molecule (icon and/or text) on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> Help molecule Then bring me to the <product’s> Help page Scenario: User searches for a term that does not have a corresponding OneBox Given I am using on-site search When I submit the search And the search term does not match <string> Then do not show a OneBox Scenario: User searches for a term that matches the string for more than one OneBox Given I am using on-site search When I submit the search And the search term matches <string> for more than one product or OneBox mapping Then only show the OneBox for the first <product> it matches {code} | OneBox - OneBox E2E Testing | 2017-07-12 10:48 | 773
732735 | 12701668 | Story | h2. Requirements A web component to display OneBox content needs to be created. The component will be used on the new search page to emphasize recommended content. h2. Design * Based off Invision Mock-ups linked in Epic h2. Stakeholders * UX: [~tnolan@redhat.com] * QA: [~ihamilto@redhat.com] * Approval: [~hwindzio@redhat.com] h2. Acceptance Criteria {code} Feature: OneBox for On-Site Search Scenario: User searches for a string that is associated with a Product OneBox Given I am using on-site search When I submit the search And the search term matches <string> Then show the OneBox for <product> And display it at the top of the search results And show the <product> information in the box And display only the links that have corresponding pages on the website Scenario: User selects the Title of the product on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> Title Then bring me to the <product’s> Overview page Scenario: User selects the View Downloads button on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> View Downloads button Then bring me to the <product’s> Download page Scenario: User selects the Hello World! molecule (icon and/or text) on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> Hello World! molecule Then bring me to the <product’s> Hello World! page Scenario: User selects the Docs and APIs molecule (icon and/or text) on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> Docs and APIs molecule Then bring me to the <product’s> Docs and APIs page Scenario: User selects the Help molecule (icon and/or text) on a Product OneBox Given I am provided with a <product> OneBox When I select the <product> Help molecule Then bring me to the <product’s> Help page Scenario: User searches for a term that does not have a corresponding OneBox Given I am using on-site search When I submit the search And the search term does not match <string> Then do not show a OneBox Scenario: User searches for a term that matches the string for more than one OneBox Given I am using on-site search When I submit the search And the search term matches <string> for more than one product or OneBox mapping Then only show the OneBox for the first <product> it matches {code} h2. Review Steps * View the rhdp-onebox component on the search page * Check for matched terms that the onebox should show * Check that the onebox does not show for unmatched terms | OneBox - OneBox Component | 2017-07-12 10:47 | 773
732738 | 12701578 | Story | h2. Problem # Visit https://developers.redhat.com/products/cdk/download/ # Observe that it's unclear what download artefact you will get when clicking on 'DOWNLOAD'. Is it the Linux, Mac or Windows one? Also: # Visit: https://developers.redhat.com/downloads/ # Observe that it's unclear what artefact you will get by clicking on any of the 'DOWNLOAD' CTA buttons. h2. Requirements Provide a solution to make it clear to the user what download they will get when clicking on these links. | Make download CTA's clearer on what artefact is linked to | 2017-07-12 05:17 | 1
732740 | 12701516 | Story | h2. Requirements The ".NET" Topic title has been updated to ".NET Core", the dropdown menu should match the title of the page. h2. UX & VD Work N/A h2. Stakeholders * Business: [~mguerett] h2. Acceptance Criteria {code} Feature: DEVELOPER-4298 Topics sub menu should include ".NET Core" and not ".NET" Scenario: Topics submenu contains the correct name for .NET Core Given a page on the website contains the header menu When I click Topics Then I should see ".NET Core" and not ".NET" {code} h2. Review Steps Run through the acceptance criteria. h2. Additional Information Tests in the Primary Navigation suite need to be updated. | Update RHD Topics pull down to be ".NET Core" | 2017-07-11 15:31
732741 | 12701487 | Story | ¦¦Actions Items¦¦Status¦¦ ¦Comment From [~hwindzio@redhat.com] in DEVELOPER-4186 "Yes, although I'm noticing in last week's deck that the screenshot in slide 7 is better than slide 8: https://docs.google.com/presentation/d/1ciZ7NPhfP9WXKtdaYBUQ1V6OeKXh5kaIVjFH-RJcFUc/edit#slide=id.g1e8eb45b58_0_23 Slide 7 is easy to read the numbers, whereas slide 8 is hard to read numbers. Any way to get them both looking consistently easy to read?"¦Done¦ ¦Add Month over Month Product Downloaders¦Done¦ | RHD Weekly Dashboard 14 July 2017 | 2017-07-11 10:28
732743 | 12701217 | Story | h2. Requirements Create a JSON representation of the data contained here: https://docs.google.com/spreadsheets/d/1vAo97loW7nPgLDRKnOoDVxTweBYDANYcSOVIAU9bIp8/edit#gid=2145207931 h2. Design * NA h2. Stakeholders * Engineering-only h2. Acceptance Criteria * JSON file is created and matches data in Sheet * JSON file is accessible from a URL on the site h2. Review Steps * Navigate to the JSON file's URL /rhdp-apps/onebox/onebox.json | OneBox - Create JSON file for config | 2017-07-10 12:20 | 773
732744 | 12701201 | Story | h2. Requirements A site exists where people can track current and historical PageSpeed Insight (https://developers.google.com/speed/pagespeed/insights/) scores for web properties. The tool should provide details of performance improvements recommended. h2. Design * NA h2. Stakeholders * Engineering-only h2. Acceptance Criteria * Site exists * List of pages presented on landing page ** Data includes pages tracked, current data, and current recommendations ** Allows adding new pages ** Each page has a button to update scores and store them (manual update) h2. Review Steps * URL TBD * Navigate to page * Add a page * Perform manual data update * View data display | Create a tool to monitor PageSpeed score daily (MVP) | 2017-07-10 11:21 | 201
732747 | 12701184 | Story | h2. Requirements As part of DEVELOPER-4150 I added quite a lot of unit-tests to Blinkr. However we need more. h2. Design * No new design needed h2. Stakeholders * Engineering-only h2. Tasks: * Finish off unit-tests for remaining untested classes (that can currently be tested). * TODO: List classes untested. * Have Rob and Jason cast an eye on the current tests. h2. Review Steps * Maintainer of Blinkr is happy with bug-fixes, improvements and unit-tests. | Finish off unit-tests | 2017-07-10 10:24 | 787
732302 | 12674368 | Story | Currently the setup of the staging virtual machine is completed by hand following a set of instructions that are maintained in a Git repository. To facilitate hand-over of the RHD website infrastructure to Lukas and to enable full support from IT, we need to puppetize the setup in a manner that is compliant with IT supported puppet infrastructure. Once this is done, all changes to the configuration of the staging VM should be raised as pull requests on the puppet Git repository. h2. Stakeholders: * [~lkoranda@redhat.com] h2. Acceptance Criteria: {code} Given that I have applied the `developerdrupal` puppet module to the staging VM Then the staging VM should be configured correctly to run and deploy Drupal Given that I am looking to apply the puppet module to the production VM Then I can refer to the staging documentation to determine how to do it {code} h2. Review steps: * Log onto the new staging VM and puppet apply the `developerdrupal` module to determine that all configuration is managed by Puppet * Verify that the new staging VM hosts Drupal as expected | Build: Staging VM setup should be managed by IT supported puppet | 2017-02-02 06:45 | 674
732305 | 12674367 | Story | Currently the setup of the production virtual machine is completed by hand following a set of instructions in a Git repository. To facilitate hand-over of the RHD website infrastructure to Lukas and to enable full support from IT, we need to puppetize the setup in a manner that is compliant with IT supported puppet infrastructure. Once this is done, all changes to the configuration of the staging VM should be raised as pull requests on the puppet Git repository. *Definition of Done* * The configuration of the production VM should be managed by IT supported puppet scripts * All puppet configuration is stored in a Git repository under the redhatdevelopers project * Changes to the configuration are made through a pull-request mechanism * It is well documented how changes are applied to the production VM. | Build: Production VM setup should be managed by IT supported puppet | 2017-02-02 06:45 | 674
732752 | 12700837 | Epic | h2. Overview This is a standard 'grouping' Epic added every quarter. It groups together a set of improvements around 'Technical SEO' that are planned for completion within the quarter. We classify 'Technical SEO' as engineering improvements that need to be made to the website platform, rather than the content. For example, ensuring every webpage's HTML contains meta-data needed to help Google crawl the site. By contrast, it doesn't cover 'Content SEO' which is about making content changes to improve SEO. For example, changing the content on a page to make it rank more highly for important keywords. h2. Team UX: Done on a per-story basis. VD: Done on a per-story basis. Eng: [~ldary24] h2. Additional Information As this is a 'grouping' epic, further information (such as wireframes and VD mockups) is added to individual stories, where needed. | Technical SEO Improvements (Q3FY18) | 2017-07-06 14:37 | 201
732758 | 12700706 | Story | Looking at Panelizer and Panels, there seems to be a wide range of things it supports. We need to look into it some more to determine if we can use for complex things like the homepage. h2. Definition of Done Determine if we can recreate the homepage using Panels/Panelizer/Lightning Layout. One of three outcomes are expected: 1) Yes, we can easily recreate the homepage using this strategy 2) No, we cannot easily recreate the homepage 3) We can recreate the homepage with some caveats (list those caveats) | SPIKE: Using Panels and Panelizer for complex layouts | 2017-07-05 12:38 | 1
732778 | 12693117 | Story | Add the following activities from the parent epic to the scoring model. Register for contributor program CTA for reporting an issue (security or website) h2. Requirements Accurately scoring user interaction for third-party apps is nearly impossible if they are housed in an iframe or separate window. We need to check Google Forms and Jira Issue reporting for events we can listen and attach to. If nothing is available, we need to find alternatives that will allow us to track things better (e.g. - Red Hat dynamic forms through eloqua) h2. Design * NA h2. Stakeholders * Analytics - [~akandel@redhat.com] * Approval - [~hwindzio] * Form Changes - [~jessk_jira] h2. Acceptance Criteria * Site is accurately tracking third-party app interactions * Where possible, switch to alternative methods for more accurate tracking h2. Review Steps * Utilize Adobe Analytics to view third-party interaction metrics | Onsite third party interaction (Katacodas progress) | 2017-05-19 09:13 | 1
732781 | 12700455 | Story | Once the current Stumpjumper configuration has been replicated via DEVELOPER-4008, the next stage is to deploy an instance of the VM managed by Vagrant onto Stumpjumper itself to replace Stumpjumper as the primary build slave for the RHDP project. h3. Stakeholders * [~lkoranda@redhat.com] h3. Acceptance Criteria {code} Given that I have checked out the RHDP Jenkins slave configuration repository on Stumpjumper And I have installed Vagrant And I have installed KVM Then I should be able to launch an Ansible managed VM to replace Stumpjumper as the current RHDP Jenkins build slave {code} h3. Review Steps * SSH to stumpjumper, going into the checkout of the Ansible managed configuration. Run `vagrant ssh` to ensure you can connect to the new Jenkins build slave. * Verify that Jenkins slaves cic-rhd-01 and cic-rhd-02 report as online via the https://redhat-dev-jenkins.rhev-ci-vms.eng.rdu2.redhat.com/ Jenkins UI | Build: Deploy Ansible managed Jenkins Slave VM on Stumpjumper | 2017-07-04 05:41 | 674
732795 | 12699557 | Story | This issue is being opened up so we have a task opened for upgrading the introduction process and help documents that are available to new users of the blog. The current materials are primarily focused on code sample insertion and some brief notes on writing for the blog, but after conferring with Jairus Mitchell, there are some improvements that could be made so that new contributors (and current contributors) have a better understanding of how to write posts to optimize search engine presence of their post, where to insert the "fold" line, adding imagery, formatting headings, etc. To offer an example of the above, I've seen some of the older posts have more than one <h1> in the post entry. I learned from Jairus that there should only be one of these in any given post. Also, David and I discussed that posts might be better off presenting all code sample blocks in the Syntax Highlighter presentation mode (the numbered line version) instead of the default <pre>/pre-formatted text display, since the latter appears to cause problems with code sample line breaks and text wrapping. If a filter is applied to accomplish this, the instructions would need to be changed accordingly. I assume more information will be available and there will be some clarity on how to proceed once Jairus, Emily and Jessica have had a chance to speak more about the SEO improvements. Again, I just wanted to get this issue on the board for reference. | Update the Introduction Process to the Blog for New Contributors | 2017-06-27 20:52 | 1
732802 | 12699285 | Story | The Program Registrations "day" dcp_query_interval is not populating graph https://app.klipfolio.com/klips/view/490e49ac0295178db526021817bf547e seems to be failing to update the graph. | Program Registrations "day" dcp_query_interval is not populating graph | 2017-06-26 10:10 | 775
732821 | 12697930 | Story | To facilitate speedy creation and testing of Ansible playbooks for DEVELOPER-4008, we will need a local development environment that. This environment should match (as closely as possible) the Stumpjumper physical machine setup. It should also be quick to get started and well documented. h2. Stakeholders: * [~lkoranda@redhat.com] h2. Acceptance Criteria: {code} Scenario: RHDP team member can checkout the Ansible development environment and run Ansible playbooks against it Given that I have checked out the Ansible development environment on my machine And I have followed the README instructions about how to complete the setup Then I should be able to boot the development environment And be able to run Ansible playbooks against the development environment Scenario: RHDP team member can easily edit and test their changes to the Ansible playbooks Given that I have checked out the Ansible development environment on my machine And I have followed the README instructions about how to complete the setup And I have followed the instructions about how to edit Ansible playbooks Then I should be able to test my Ansible playbook changes agains the development environment {code} h2. Review Steps * Checkout the development environment configuration on your machine * Ensure the development environment boots and that you can easily apply Ansible playbooks * Attempt a minor modification to the Ansible playbook and ensure that you can apply the changes by following the included instructions | Build: Create a development environment for the authoring of Ansible playbooks | 2017-06-19 05:09 | 674
732825 | 12697673 | Story | h2. Requirements As a user, I should be able to see some sort of notification when I reach the end of the results. Currently, the LOAD MORE disappears which should still occur in addition to the notification message. h2. Design See InVision link below. The "End of Results" was added to the Base Search wireframe. h2. Stakeholders UX: [~tnolan] Eng: [~ldary] h2. Acceptance Criteria h4. Scenario 1: User sees the end of the returned search results Given I am using the RHDP on-site search And I entered a search query When I reach the end of the returned results Then do not show the Load More button And show some text that says " - End of Results - " h4. Scenario 2: User gets to the end of the returned resultset, but there are more results Given I am using the RHDP on-site search And I entered a search query When I reach the end of the returned resultset And there are more results Then show the Load More button And do not show the " - End of Results - " text h2. Review Process # Go to: https://developers.redhat.com/search/?q=faq # Filter by CONTENT TYPE of "Article" - You should see about 12 as the results found number # Click LOAD MORE # Verify a notification message displays at the end of the results to indicate there are no more results. | Notification for end of results | 2017-06-15 15:59 | 739
732833 | 12697507 | Story | h2. Requirements Search is handled by web components now, so there is no need to continue to build/manage the page in Awestruct. h2. Design * NA h2. Stakeholders * Engineering-only h2. Acceptance Criteria * The Awestruct search page is set to ignore_export: true h2. Review Steps * Verify the build does not come from awestruct by changing something and running a build | Migrate /search to Drupal | 2017-06-14 12:07 | 1
732837 | 12697212 | Epic |  | Technical SEO issues (Q2FY18) | 2017-06-13 06:20 | 201
732844 | 12696996 | Story | h2. Requirements Create documentation to describe new code, new build process, and pitfalls to avoid h2. Design * NA h2. Stakeholders * Engineering-only h2. Acceptance Criteria * Documentation exists * Documentation answers primary questions h2. Review Steps * View documentation | Document New Search and Build Process Code | 2017-06-12 11:37 | 739
732847 | 12696990 | Story | h2. Requirements Users need the ability to navigate back to the top of the page after loading multiple pages worth of results. h2. Design It should look like the Customer Portal's version: !2017-06-19_12-09-36.png¦thumbnail! They use the font awesome "icon-circle-arrow-up" for the icon. Their code for styling queues: {code} height: 44px; width: 44px; padding: 10px; background-color: #333; background-color: rgba(0,0,0,0.8); -webkit-transition: opacity 0.218s; -o-transition: opacity 0.218s; transition: opacity 0.218s; font-size: 24px; line-height: 24px; vertical-align: middle; color: #fff; text-decoration: none; cursor: pointer; {code} h2. Stakeholders * UX: [~tnolan] * VD: [~jcobb@redhat.com] * Engineering: [~ldary] * Reviewer(s): [~hwindzio] h2. Acceptance Criteria * User has the ability to go back to top of page after scrolling down h2. Review Steps * perform search * load more results * scroll down * click element to go back to top | Add "Back to Top" floating link to results | 2017-06-12 11:32 | 739
732853 | 12696912 | Story | Show weekly natural traffic referrer | Organic Traffic Over Time | 2017-06-12 08:49 | 775
732854 | 12696911 | Story | Show a graph with new vs returning visitors vs returning members Use the builtin function visit count in omniture now that the unified analytics working group have decided to deprecate evar89 showing new/repeat visit. There will be discrepancies in the data given the old method was using a plugin whereas the new one use a cookie | New vs returning visitors vs returning members | 2017-06-12 08:48 | 775
732855 | 12696909 | Story | Create a fallout report for our registration form | Registration form fallout report | 2017-06-12 08:47 | 775
732856 | 12696906 | Story | Show page views avg time spent bounce rate and weighted bounce rate by url | Create bounce rate table | 2017-06-12 08:46 | 775
732857 | 12696902 | Story | Show % of trackable traffic by looking at possible detectable registrations in klipfolio v. registrations in Adobe. | % of trackable traffic | 2017-06-12 08:42 | 775
732858 | 12696900 | Story | Show RHD non registered unique visitors RHD Registrations Conversion rate between both metrics | RHD registrations/unique visitors | 2017-06-12 08:40 | 775
732859 | 12696897 | Story | show % of users that are active broken down by: Actual Projected Target | % of users that are active | 2017-06-12 08:38 | 775
732860 | 12696895 | Story | Breakdown registrations in a table showing Red Hat Developer Program OpenShift.io OpenShift Online over Net New to Red Hat Existing Red Hat Account Existing RHD Member Registrations | Create registrations breakdown | 2017-06-12 08:35 | 775
732863 | 12696829 | Story | I have suggestion to page https://developers.redhat.com/products/devstudio/docs-and-apis/ I would suggest to add default button "View as HTML" next to the button "View as" - for better user experience (in my opinion a lot of people are using online documentation). The second approach could be to have titles as links to html pages, for example: title "Release Notes and Known Issues" will be link to the https://access.redhat.com/documentation/en-us/red_hat_jboss_developer_studio/10.4/html/release_notes_and_known_issues/ | View documentation as html by default | 2017-06-12 04:24 | 1
732867 | 12696706 | Epic | Create a new 0.4.0 release of Blinkr with current bug fixes, additional features, unit-tests and replacement/additional headless browser to PhantomJS. | Blinkr 0.4.0 | 2017-06-09 10:45 | 787
732882 | 12695365 | Epic | In order to reduce manual work around the RHD Weekly Dashboard we need to automate as much as we can the process. Not only will this reduce our time spent on a repetitive activity it will also decrease the risk of manual errors. | Automate RHD Weekly Dashboard in Klipfolio | 2017-06-01 09:04 | 775
732905 | 12694817 | Story | Blinkr currently has no unit-tests at all which makes adding/fixing features very difficult. - create test site - add unit-tests for Blinkr features | Spike: Add unit-tests to Blinkr | 2017-05-30 09:09 | 787
732906 | 12694793 | Story | h2. Requirements The /products page is no longer being push in via awestruct h2. UX & VD N/A h2. Stake Holders: Dev: [~lightguard] h2. Acceptance Criteria {noformat} Feature: DEVELOPER-4149 -- Migrate /products page to Drupal Given a small change is made to the page When a build is run Then there should be no revision made to the page within Drupal {noformat} h2. Review Steps Verify the build did not push the page to Drupal 1. Make a small change to the /products page in awestruct 2. Execute a build 3. Verify there is no new revision for that page within Drupal. | Migrate /products page to Drupal | 2017-05-30 08:11 | 1
732907 | 12694792 | Story | h2. Requirements The /downloads page is no longer being push in via awestruct h2. UX & VD N/A h2. Stake Holders: Dev: [~jporter@redhat.com] h2. Acceptance Criteria {noformat} Feature: DEVELOPER-4148 -- Migrate /downloads page to Drupal Given a small change is made to the page When a build is run Then there should be no revision made to the page within Drupal {noformat} h2. Review Steps Verify the build did not push the page to Drupal 1. Make a small change to the /downloads page in awestruct 2. Execute a build 3. Verify there is no new revision for that page within Drupal. | Migrate /downloads page to Drupal | 2017-05-30 08:10 | 1
732908 | 12694791 | Story | h2. Requirements Since we've migrated to lightning and removed muliversion, we're in a great position to start using panels for things. We need to create a panels layout for the front page, migrate the front page to use this new layout, and finally no longer push the awestruct homepage. h2. Design * None h2. Stakeholders * UX - None * Eng - Jason Porter * VD - None h2. Acceptance Criteria * Panels, panelizer, and layout modules are all installed * A new layout is created for the front page * A new instance of "landing page" is created that is now the homepage * Drupal uses the new landing page instance as the home page for the site h2. Review Steps * Verify the landing page is created and used * Verify the html results in the same layout as the current page * Verify the main page in awestruct is no longer pushed | Migrate Homepage to Drupal | 2017-05-30 08:10 | 1
732909 | 12694790 | Epic | This epic covers the work required to remove Awestruct from the build pipeline. Large bits of migration work are covered by other Epics (E.g migrating code examples). This covers all the smaller things required to complete migration, and the tasks needed to remove Awestruct. | Remove Awestruct Pipeline from Build | 2017-05-30 08:09 | 1
732941 | 12693986 | Story | Add OSO and OSIO registration metrics to dashboard, similar to the way we visualize RHDP metrics in the dashboard today. | Create Combined Registration Metrics for JBD RHD OSO OSIO | 2017-05-24 08:43 | 775
732945 | 12693449 | Story | Add drop off for OSIO reg page, similar to what we do for RHDP reg page today. Keep the RHDP, OSO, and OSIO charts separate. Review all other metrics we're pulling in the dashboard today to ensure that they are not being conflated with OSO or OSIO. | Add Registration field Fallout OSIO and OSO metrics to the weekly dashboard | 2017-05-22 09:43 | 775
732965 | 12693505 | Epic | A number of items have been brought up over the past few months about the usability or stability of Drupal. This epic will seek to find and correct those issues. | Stabilize and enhance current Drupal Usability (G Train) | 2017-05-22 15:16 | 712
732977 | 12693477 | Story | h2. Requirements * In the user's profile, tell them what level they have (currently one of: basic, full). * Tell the user what their current level lets them do * Provide the user with an option to upgrade if they are not fully upgraded. h2. Design h2. Stakeholders h2. Acceptance Criteria & Testing h2. Tasks h2. Review Process | Profile level information for users | 2017-05-22 11:31 | 680
732979 | 12693475 | Story | Design: https://redhat.invisionapp.com/share/35DQIBVG4 | UI changes to the Log In page | 2017-05-22 11:28 | 728
733000 | 12691862 | Story | We should have an easy way to select a related product on the Drupal content form so that the related product information can be added to content types such as cheat sheets, books, videos, etc. The card should contain 4 elements: # Heading for the card - In this instance, it would be Related Product, but it could be related Topic or something else in the future. # Title of the item being promoted - Initially this would be the Product Name. Bonus points for having this as a drop-down or autocomplete for exact match. # Optional description text - Up to 3 lines # Light CTA for "Learn more" - I think this would be exactly the same for all. Initial implementation would be on the Cheat Sheets and Book Drupal pages. | Include a way to add related product to Drupal content pages | 2017-05-11 15:54 | 712
733050 | 12688456 | Story | We need to ensure that all production content is synced to the staging environment so that we can run content specific tests in staging before applying them to production. *Definition of Done* * All content from production is synced to staging on a daily basis * It is possible to sync content from production to staging "on-demand" via Jenkins | Build: Ensure all production content is synced to staging environment | 2017-04-20 08:24 | 674
733054 | 12688234 | Story | To support the puppetization of the current staging and production VMs, we're going to need a development environment that allows those authoring the puppet scripts to easily create, edit and test the current puppet setup in their local development environment. *Definition of Done* * Developers authoring puppet scripts can easily create, edit and run puppet scripts in their local development environment * It is well documented how to use the puppet development environment | Build: Setup development environment to support authoring of puppet scripts | 2017-04-19 07:27 | 674
733055 | 12688191 | Story | Before beginning any puppetization, we need to understand fully ITs supported puppet infrastructure so that we: * Are compatible and produce something that is supported * Store our puppet scripts in the correct location * Understand the IT best practices (if any) *Definition of Done* * We understand how ITs puppet infrastructure works and what is supported * We understand how we can run the IT puppet scripts | Spike: Understand IT puppet infrastructure | 2017-04-19 07:14 | 674
733056 | 12688183 | Story | As part of the handover of the current RHD website infrastructure, we need to document the current setup of our main Jenkins slave stumpjumper. Documentation to include: * How to setup the current Stumpjumper machine * Any particulars of the setup that are useful to know and how they link to the jobs that run on Stumpjumper Documentation should be stored within this area of Mojo: https://mojo.redhat.com/community/old_docspace/bu/middleware/jbossorg/developerredhatcom/infrastructure *Definition of Done* * Documentation on the current Stumpjumper setup is in Mojo * The documentation has been reviewed and signed-off by [~lkoranda@redhat.com] | Build: Document Stumpjumper setup in Mojo | 2017-04-19 07:00 | 674
733057 | 12688180 | Story | As part of the handover of the RHD website infrastructure, we need to document the current Jenkins setup. Documentation to include: * What does each job do * Any special configuration for each job that would be useful to hand-over Documentation should be stored within this area of Mojo: https://mojo.redhat.com/community/old_docspace/bu/middleware/jbossorg/developerredhatcom/infrastructure *Definition of Done* * Documentation about the current Jenkins setup is in Mojo * Documentation has been reviewed and signed-off by [~lkoranda@redhat.com] | Build: Document Jenkins setup in Mojo | 2017-04-19 06:53 | 674
733058 | 12688179 | Story | In order to facilitate hand-over of the current RHD website build and deployment pipeline, it should be fully documented in Mojo. Documentation should include: * What are the components of the pipeline * What does each component do and why does it do it * What jobs in Jenkins map onto the build and deployment pipeline Documentation should be stored within this area of Mojo: https://mojo.redhat.com/community/old_docspace/bu/middleware/jbossorg/developerredhatcom/infrastructure *Definition of Done* * The current build and deployment pipeline has been documented in Mojo * Documentation has been reviewed and signed off by [~lkoranda@redhat.com] | Build: Document current build and deployment pipeline in Mojo | 2017-04-19 06:51 | 674
733059 | 12688176 | Story | As part of the hand-over of the RHD website infrastructure, we need to provide comprehensive documentation of the current staging and production VM. This should include: * What are the sizings of the VM * What software is installed and why * What network mounts are used * Filesystem locations of important files and folders Documentation should be contained within this area of Mojo: https://mojo.redhat.com/community/old_docspace/bu/middleware/jbossorg/developerredhatcom/infrastructure *Definition of Done* * Documentation of the current infrastructure is available within Mojo * Documentation has been reviewed and signed-off by [~lkoranda@redhat.com] as covering everything he needs | Build: Document production and staging infrastructure in Mojo | 2017-04-19 06:46 | 674
733060 | 12688153 | Epic | The current RHD website infrastructure and build pipelines needs to be handed over to Lukas for management by the end of August. This epic captures all of the work required to get the current infrastructure and build pipeline into a state where it can be fully managed by Lukas. | Handover of RHD infrastructure and build pipeline | 2017-04-19 05:38 | 674
733084 | 12687496 | Story | h2. Requirements Upon downloading media from RHD, the user is directed to a thank you page. The "Thank You" page thanks them for downloading the specific product and gives them the ability to report an issue if something unexpected happens with the download. Question mark at the end of the URL in download manager is required otherwise it will redirect to a 404. h3. *Additional Info from David Hladkey* I think the best solution would be creating a thank you page for all the "Media" downloads. When redirecting to the thank you page Download Manager adds following useful information so the page can be rendered nicely: tcUser - the name of the user, that is trying to download stuff (unless it is anonymous download) tcDownloadFileName - name of the file being downloaded tcRedirect - delay time (milliseconds) when the download is about to start p - name of the product to be downloaded (e.g. "Media: Docker Cheat Sheet") pv - name of a product version (it can help if there are multiple versions of the file within the product version) h2. Stakeholders * UX - [~tnolan@redhat.com] * Engineering - [~dcoughlin1] * VD - ? * Review - [~hwindzio@redhat.com] h2. Acceptance Criteria * User sees thank you page upon downloading media items * All links point to appropriate pages h2. Review Steps * click all links to make sure they go to expected pages * activate media download and observe appropriate thank you page | Create thank you page component for media downloads | 2017-04-12 14:31 | 742
733085 | 12687495 | Story | h2. Requirements The automatic download should trigger when the user goes to the Media Download Confirmation page on both desktop and mobile devices. (https://developers.redhat.com/media-download-confirmation/) Currently, the user must use the direct link from the alert message when on desktop. * It does not work in Chrome on a Mac. * I have not tested other OS/browser combos or mobile devices. * Example URL for testing: https://developers.redhat.com/media-download-confirmation/?tcUser=Tiffany+Nolan&tcDownloadFileName=advanced_eap7_cheat_sheet_r2v1.pdf&tcRedirect=5000&tcSrcLink=https://developers.redhat.com/download-manager/content/origin/files/sha256/a0/a0aa40c62274bd34dcec2b23e53424f58cb065650fda4c9cc02ebf589fbee4b7/advanced_eap7_cheat_sheet_r2v1.pdf&p=Media:+Advanced+EAP+Cheat+Sheet&pv=Advanced+EAP+Cheat+Sheet&tcDownloadURL=https://access.cdn.redhat.com/content/origin/files/sha256/a0/a0aa40c62274bd34dcec2b23e53424f58cb065650fda4c9cc02ebf589fbee4b7/advanced_eap7_cheat_sheet_r2v1.pdf?_auth_=1507656456_1ebecf745a0374c4348daff726f1d379 h2. Design Not needed. h2. Stakeholders UX: [~tnolan] Engineering: TBD h2. Acceptance Criteria h4. Feature: Media downloads Scenario: User follow the login/registration flow and lands on the Media Download Confirmation page *Given* I followed the login/registration flow for a media asset (cheat sheet or book) *And* I am authenticated *When* I land on the Media Download Confirmation page *Then* I should see the PDF file being automatically downloaded in my browser window. h2. Tasks * Research why the download does not trigger immediatly. * Fix the issue h2. Review Process * Go to: https://developers.redhat.com/media-download-confirmation/?tcUser=Tiffany+Nolan&tcDownloadFileName=advanced_eap7_cheat_sheet_r2v1.pdf&tcRedirect=5000&tcSrcLink=https://developers.redhat.com/download-manager/content/origin/files/sha256/a0/a0aa40c62274bd34dcec2b23e53424f58cb065650fda4c9cc02ebf589fbee4b7/advanced_eap7_cheat_sheet_r2v1.pdf&p=Media:+Advanced+EAP+Cheat+Sheet&pv=Advanced+EAP+Cheat+Sheet&tcDownloadURL=https://access.cdn.redhat.com/content/origin/files/sha256/a0/a0aa40c62274bd34dcec2b23e53424f58cb065650fda4c9cc02ebf589fbee4b7/advanced_eap7_cheat_sheet_r2v1.pdf?_auth_=1507656456_1ebecf745a0374c4348daff726f1d379 * Confirm the file downloads in the browser | Research why the code for the Thank you message is not firing for media downloads | 2017-04-12 14:29 | 742
733086 | 12687494 | Epic | h2. Requirements https://docs.google.com/document/d/1ZVxDu_2i89n1Gur5dfk6JqHSd6AR8tT9_eE74nui1kA/edit# h2. Design Refer to attached InVision Project h2. Stakeholders Requirements: [~tnolan@redhat.com] UX: [~tnolan@redhat.com] VD: James (View only) Engineering: [~dcoughlin1] h2. Acceptance Criteria h3. Feature: Confirmation page for media downloads Scenario 1: User downloads a media asset delivered through the Download Manager Given User initiates a download from Download Manager And the download type is a media asset When the download initiates Then the user should be redirected to the media downloads confirmation page And the download should occur on the media downloads confirmation page Scenario 2: User interacts with the “Tell us about it” link Given User is on the media downloads confirmation page When the user selects the “Tell us about it” link Then open the JIRA Raise a bug form in a pop-up window Scenario 3: User’s download doesn’t initiate Given User is on the media downloads confirmation page When User doesn’t see the download in their browser or the download doesn’t initiate Then the user can use the always visible “direct link” hyperlink in the Information Alert box. Scenario 4: Name of download doesn’t include “Media:” Given User is on the media downloads confirmation page When the name of the download asset is displayed in the Heading Then it should only include the name and not any additional information such as the text “Media:”. | Improve user experience for media downloads | 2017-04-12 14:24 | 742
733093 | 12687446 | Story | Currently, someone can go to the 'Help' tab, and it displays StackOverflow and forum questions. That page should tell folks to post their questions to StackOverflow, and provide the tags to post with. It could read something like: "We'd like to help you find an answer to your technical question on EAP. You can post your question on StackOverflow using the tags jboss-eap6, jboss-eap7. Your questions will be shared on developers.redhat.com." Here are the tags associated with each product https://docs.google.com/spreadsheets/d/1CTU6cV_HriqfZMLcbUrzlhumrrZ3ovpkzckXxd-x6KU/edit#gid=0 It's on the sheet 'tag mapping' under column D. We should start with devtools products only (as the other products have yet to be cut over 100% to StackOverflow): -OpenJDK -CDK (for containers) -RHEL (for dts) -JBDS | We should let folks know to post their questions to StackOverflow on the 'Help' tab | 2017-04-12 09:59 | 41
733100 | 12686918 | Story | Stumpjumper is the primary Jenkins slave enabling pull request builds on the RHDP project. It is therefore an important part of the project infrastructure. Currently the setup of this host is managed entirely by hand, so in the event of needing to re-build/re-configure Stumpjumper it is an entirely manual, lightly documented process. The current setup is documented in [Mojo¦https://mojo.redhat.com/docs/DOC-1139489-jenkins-stumpjumper-slave-setup]. However to move the project away from manual re-building/re-configuration, we would like to move these configuration steps into Ansible playbooks. This will aid in the hand-over of the RHDP build pipeline to Lukas. *Note:* The ideal solution here would be to use IT managed puppet, however because of Stumpjumper's location in a Boston lab, this will not be possible. Therefore it was agreed that the simplest self-managed solution would be a set of Ansible playbooks that can be run to re-create the Stumpjumper configuration. h2. Stakeholders * [~lkoranda@redhat.com] h2. Acceptance Criteria {code} Given that I have the Ansible playbook repository checked out on my machine And I have followed the README instruction on how to run them Then I should be able to quickly re-build the current Stumpjumper configuration on the local VM {code} h2. Review steps * Checkout the Ansible playbook repository and apply the changes to the development environment in the first instance to ensure they work as expected | Build: Stumpjumper setup should be managed through Ansible | 2017-04-10 08:14 | 674
733112 | 12686395 | Story | See https://docs.google.com/spreadsheets/d/15OTlWeWCXbSGIUlNao8qOYenYUhGY71WKGd0aEFcqc0/edit#gid=1441024375. These are all on blog pages. | Fix broken images on the Blog | 2017-04-06 06:35 | 201
733113 | 12686394 | Story | h2. Requirements A site exists where people can track current and historical PageSpeed Insight (https://developers.google.com/speed/pagespeed/insights/) scores for web properties. The tool should provide details of performance improvements recommended. h2. Design * NA h2. Stakeholders * Engineering-only h2. Acceptance Criteria * Site exists (hosted on Open Platform) * List of web properties (groups of sites/pages) is presented on landing page * Web property page displays list of sites/pages tracked, historical data, and current recommendations * Site page should show pages tracked and their historical data and current recommendations. * Page detail page should show historical data, recommendations * All pages should have the ability to edit related tracking frequency and details where appropriate. h2. Review Steps * URL TBD * Navigate to page * Add a property, site, page * Perform manual data update * View data display | Create a tool to monitor Lighthouse score daily | 2017-04-06 06:34 | 201
733116 | 12686392 | Story | h2. Requirements Create JIRA stories to address all common deficiencies on important (listed below) pages. Aim for a green rating (85+) for optimizations. h2. Design * NA h2. Stakeholders * Engineering-only h2. Acceptance Criteria * Items from PageSpeed scoring from important pages are aggregated into JIRA stories h2. Review Steps * Check the following pages in PageSpeed Insights (https://developers.google.com/speed/pagespeed/insights/?url=) ** https://developers.redhat.com ** https://developers.redhat.com/products/rhel/overview/ ** https://developers.redhat.com/products/rhel/download/ ** https://developers.redhat.com/products/rhel/hello-world/ ** https://developers.redhat.com/products/rhel/docs-and-apis/ ** https://developers.redhat.com/products/rhel/help/ ** https://developers.redhat.com/products/rhel/learn/ ** https://developers.redhat.com/products/rhel/buzz/ ** https://developers.redhat.com/search?q=containers ** https://developers.redhat.com/blog ** https://developers.redhat.com/blog/2016/03/31/no-cost-rhel-developer-subscription-now-available/ ** https://developers.redhat.com/downloads ** https://developers.redhat.com/topics/dotnet ** https://developers.redhat.com/promotions/kubernetes-cheatsheet/ ** https://developers.redhat.com/articles/no-cost-rhel-faq ** https://developers.redhat.com/stack-overflow/ ** https://developers.redhat.com/community/contributor/ ** https://developers.redhat.com/devnationlive * Common errors should be logged as JIRA issues and assigned to the appropriate person | Plan Improvements to PageSpeed score for important pages (mobile & desktop) | 2017-04-06 06:33 | 201
733119 | 12686391 | Story | h2. Requirements PageSpeed score on the blog is greatly impacted by image sizes and script minimization. Find an effective way to handle this using a Wordpress plugin. h2. Design * NA h2. Stakeholders * Engineering-only h2. Acceptance Criteria * PageSpeed score should have a noticeable up-tick when we have fewer issues with images and asset sizes h2. Review Steps * View PageSpeed Insights score for blog pages | Improve pagespeed score for blog (mobile & desktop) | 2017-04-06 06:31 | 201
733121 | 12686389 | Story | h2. Requirements Fixing the rel=canonical tag usage is also a high priority fix. There are 1076 pages that are missing the tag entirely. When it is used the current usage is a self-referencing "/." and it is unclear how Google parses relative URLs. RHDP should implement the full path URL on all pages as the self-referencing rel=canonical tag. h2. Design * NA h2. Stakeholders * Engineering-only (results will reflect for analytics and SEO though) h2. Acceptance Criteria * All pages have canonical reference to the full URL where the page exists (Drupal v. Export) * All pages, which are not duplicated content, should have the href attribute equal the base URL (no query string or hash) of the page. Examples ** https://developers.redhat.com/resources/#!type=code_artifact canonical is https://developers.redhat.com/resources/ ** https://developers.redhat.com/products/devsuite/hello-world/?... canonical is https://developers.redhat.com/products/devsuite/hello-world/ h2. Review Steps * Check affected pages called out by Cafelli: https://docs.google.com/spreadsheets/d/15OTlWeWCXbSGIUlNao8qOYenYUhGY71WKGd0aEFcqc0/edit#gid=3485059 | Update 'rel=canonical' to use absolute paths and be present on all pages | 2017-04-06 06:29 | 201
733126 | 12686386 | Story | Review https://developers.redhat.com/sitemap.xml and remove any entries that should not be there. For example: {code} <url> <loc>https://developers.redhat.com/node/805</loc> <lastmod>2016-12-05T05:52:14-08:00</lastmod> <priority>0.5</priority> </url> {code} In this case, that page actually exists. So the fix there is probably to prevent it being exported. *Note:* Please take a look in the sitemap.xml for other stuff that shouldn't be there. h2. Definition of Done There are no 'node' entries in the sitemap.xml file | Remove 'node' pages from sitemap.xml | 2017-04-06 06:27 | 201
733128 | 12686385 | Story |  | Provide sitemap for Blog to Google Search Console | 2017-04-06 06:26 | 201
733130 | 12686384 | Story |  | Provide sitemap for main site to Google Search Console | 2017-04-06 06:25 | 201
733152 | 12684775 | Epic | Additional information * [PDD Experience Details¦https://docs.Google.Com/document/d/17hm4jggbo0gq4sxyeicz6pbxlwzbntrpkqnkkl9ynp8/edit#heading=h.F44o1tysyml3] h2. Requirements Take the [Cafelli SEO report¦https://docs.google.com/spreadsheets/d/15OTlWeWCXbSGIUlNao8qOYenYUhGY71WKGd0aEFcqc0/edit#gid=1196233685] and fix the important issues. There is also a presentation that explains what needs fixing and why: https://drive.google.com/open?id=0B9K-oe7rbRH8VENYX1JhRHNtLWs. In particular: * Fix all broken links ** Some exceptions may be allowed if the content is hard to update and has minimal views * Put permanent (301) redirects in place for the old blog to the new location * Upload sitemap.xml files for the blog and main site to Google Search Console. * Change temporary (302) redirects to permanent (301) redirects. * Update rel=canonical to use absolute paths and be present on all pages * Remove rel=prev and rel=next from blog posts. * Improve pagespeed score for blog (mobile & desktop), main site (mobile and desktop). ** Aim for green on all high-value pages ** Monitor these pages automatically to ensure they continue to stay fast. * Fix broken image links | Technical SEO issues (Q1FY18) | 2017-03-28 09:22 | 201
733164 | 12684360 | Story | The styling for the blog currently uses a mix of CSS, including: * 2 stylesheets imported from the main RH Developer Site * The parent theme's/Red Hat blog default stylesheets * Some custom styles applied specifically to the RH Developer Blog. The custom RH Blog stylesheet has grown rather large and should be converted to a compiled format, whether that's via LESS, SASS or SCSS. | Convert Custom RH Blog CSS To A Compiled, Minified Format | 2017-03-24 09:43 | 201
733186 | 12681516 | Story | As an author, editor, or admin, I can select "crop" and resize any or all of the 4 sides of an image. This will omit displaying portions of the image that have been cropped. I can later re-crop back to original state. I think this ends up being more of a spike. We already have cropping available to admins, but I'm not sure how to use it and to what extent this is usable for what [~mguerett] wants. h2. Design N/A h2. Stakeholders Business: [~mguerett] Engineering: [~jporter@redhat.com] h2. Tasks * Explore the cropping capabilities already installed * Document the tools available * Expose the cropping tools to users h2. Acceptance Criteria * Documentation is created for users * Users can use the cropping tools | Need to crop images that are in a drupal document | 2017-03-13 08:52 | 712
733222 | 12678100 | Epic | As a visitor, I want to: *click a 'Try It Now' button, which connects me to an online IDE with a Red Hat product running a quickstart. Note, this is work that we are contracting Codenvy to do with Che Additional Information * [PDD Experience Details¦https://docs.google.com/document/d/17hM4jgGbO0Gq4sXYEiCZ6pbXLwzbNtrPKqnkKL9YNp8/edit#heading=h.tw5q03r4qphd] * Requirements Document * [Design¦https://redhat.invisionapp.com/share/6N9LPPVUR#/253639813_Try_it_Now_-_EAP_Download_Page__-_Desktop_HD] h2. MVP Requirements * Only being launched for the EAP product, kitchensink quickstart * We need to add a CTA Bar to the EAP Downloads page. The bar will appear directly under the product header section. * We need to be able to turn the display of the bar on/off. Recommendation is to use Adobe Target for this since both [~akandel@redhat.com] and [~ldary] can configure what experiences are active/inactive. * Ideally, we'd also like to be able to display the CTA Bar to various geographic regions as part of a slow roll-out. - Further reason we should use Target. h2. Team Requirements: [~hwindzio@redhat.com] UX: [~tnolan] VD: Tiffany consulted with [~jbrock@redhat.com] Engineering: [~dcoughlin1] | Add a 'Try It Now' feature to product(s) | 2017-02-21 08:39 | 744
733247 | 12677048 | Epic | h2. Description Currently the RHD Drupal server is only accessible on the VPN. An export process takes a snapshot of the site’s content and places it on an external-facing web server. This architecture was setup for simplicity and was the only option available to meet the deployment date requested by the Developer Program. h2. Benefits Off-VPN access for content contributors | Allow external content contributions to Drupal | 2017-02-15 13:40 | 1
733249 | 12676837 | Epic | As a member, I want channels of communication so that I can provide feedback to the author and ask questions or have a discussion. For example, discussions or vote up/down features. h2. Additional Information * [PDD Experience Details¦https://docs.google.com/document/d/17hM4jgGbO0Gq4sXYEiCZ6pbXLwzbNtrPKqnkKL9YNp8/edit#heading=h.dufdlhgbfzv7] * [Requirements Document¦https://docs.google.com/document/d/1-uyPrQnZQWYOLfF86eIrIDXfT19PBrZKy89ohRUJT5M/edit#heading=h.cjvnrpmhwhjw] * InVision Project for Wireframes * Visual Design Mock-up(s) h2. Team Requirements: [~hwindzio] UX: [~gdoyle-1] VD: [~jbrock@redhat.com] Engineering: [~dcoughlin1] h2. Acceptance Criteria h3. Scenario 1 Scenario: User navigates to a <product’s> Hello World page Given I am on a <product> Hello World page When I get to the page Then show the private comment organism And display it at the bottom of the left tab menu h3. Scenario 2 Scenario: User navigates to a <product’s> Hello World page on a mobile device Given I am on a <product> Hello World page When I get to the page Then show the mobile private comment organism And display it below the menu h3. Scenario 3 Scenario: User scrolls down a <product’s> Hello World page Given I am scrolling down a <product> Hello World page When I scroll Then make the private comment organism sticky And display it on the left side, only changing location vertically h3. Scenario 4 Scenario: User scrolls down a <product’s> Hello World page Given I am scrolling down a <product> Hello World page When I scroll Then do not change the location of the mobile private comment organism h3. Scenario 5 Scenario: User selects the comment organism on a <product’s> Hello World page Given I am on a <product> Hello World page When I select any area of the comment organism Then automatically take me down the page to the feedback form h3. Scenario 6 Scenario: User is brought to the bottom of the page to the feedback form Given I selected the comment organism When I get to the feedback form at the bottom of the page Then show a line separating the feedback form from the rest of the page And display a question “Was this helpful?” And display it underneath the line, centered on the page And display a textbox And display it underneath the question, centered on the page And display a “Submit” CTA And display it underneath the textbox, left-aligned with the question and textbox h3. Scenario 7 Scenario: User answers “Was this helpful?” Given I am at the feedback form of a <product’s> Hello World page When I get to the question “Was this helpful?” Then display two medium CTAs “Yes” and “No” And display them to the right of the question Then allow me to select an answer And display the CTA as filled upon hover and selection h3. Scenario 8 Scenario: User fills out the textbox Given I am at the feedback form of a <product’s> Hello World page When I get to the empty textbox asking for details about my experience Then allow me to type an unlimited amount of characters into the box And display a “Submit” heavy CTA underneath it h3. Scenario 9 Scenario: User submits a feedback form Given I am at the feedback form of a <product’s> Hello World page When I submit my feedback Then display a success alert above an empty state form | Feedback on content | 2017-02-14 16:47 | 729
733266 | 12676672 | Epic | As a visitor, I want to: * highlight a section of text, with a quick-view option to post the quoted text to a social media channel of my choice Example links: * http://www.strategy-business.com/article/10-Principles-of-Strategy-through-Execution * http://www.nirandfar.com/2016/01/laptop-zen-creating-distraction-free-desktop.html h3. Additional Information * [PDD Experience Details¦https://docs.google.com/document/d/17hM4jgGbO0Gq4sXYEiCZ6pbXLwzbNtrPKqnkKL9YNp8/edit#heading=h.vkyagacs254v] * [Requirements Document¦] * InVision Project for Wireframes * Visual Design Mock-up(s) h3. Team Requirements: [~hwindzio] UX: [~tnolan] VD: [~jcobb@redhat.com] Engineering: [~ldary24] | Sharing quoted content on social media | 2017-02-14 09:09 | 770
733271 | 12676459 | Epic | As a visitor using search, if there is a product related to my search query, I want to easily see it, so that I can quickly access the product info or download. h2. Requirements * [PDD Experience Details¦https://docs.google.com/document/d/17hM4jgGbO0Gq4sXYEiCZ6pbXLwzbNtrPKqnkKL9YNp8/edit#heading=h.5verzwiu6iof] * [Requirements Document¦https://docs.google.com/document/d/1yoX6Sa77NFy8I7yXaHSiQscdBNN-MxNJ1wk2FXPhoi8/edit#heading=h.dgsglhkiq1he] h2. Design * [InVision Project for Wireframes¦https://redhat.invisionapp.com/share/9SCDU0TDM] - Also attached below via JIRA InVision Plug-in * [Visual Design Mock-up(s)¦https://redhat.invisionapp.com/share/9SCDU0TDM#/screens/244794049] h2. Stakeholders Requirements: [~hwindzio] UX: [~tnolan@redhat.com] VD: [~jbrock@redhat.com] - [~jcobb@redhat.com] Engineering: [~ldary] h2. Acceptance Criteria Google doc with initial test scenarios: https://docs.google.com/document/d/1KwS6eyPuQ172CakGbr2n4DYi2zv6rj6K6ZBr1qoigUM/edit?ts=595d0228#heading=h.6hfhddo0b0mx | Add onebox for related product to search results | 2017-02-13 13:17 | 773
733278 | 12676444 | Story | As a visitor using search, I want to see recommended items and name match suggestions so that I can quickly find the item I'm looking for. [Typeahead Search slide deck¦https://docs.google.com/a/redhat.com/presentation/d/1WtfW3MjS1uf8jYB7Qg5fj5zPV10yahnDPwWpjyH-kZU/edit?usp=sharing] h3. Additional Information * [PDD Experience Details¦https://docs.google.com/document/d/17hM4jgGbO0Gq4sXYEiCZ6pbXLwzbNtrPKqnkKL9YNp8/edit#heading=h.5verzwiu6iof] * [Requirements Document¦https://docs.google.com/a/redhat.com/document/d/18443IGA55w2MzjmDpn0SaIPc0i9BZIFo4wQ6CGPcKlE/edit?usp=sharing] * InVision Project Wireframe * Visual Design Mock-up(s) | Add typeahead to search box | 2017-02-13 11:19 | 1
733283 | 12676201 | Story | Currently we have 18 internal and 62 external broken links. *NOTE* the get-started links should all be fixed. So ignore those in the report. h2. Definition of Done # There are 0 internal broken links # We have fixed external broken links where possible, and notified 3rd parties of broken URL's. | Fix RHD broken links | 2017-02-13 05:45 | 201
733364 | 12673926 | Story | Please see DEVELOPER-3813 for the full back-story. Essentially it would appear that if a user creates a custom shortcut list, then our approach to synchronising the configuration of Drupal fails. In the PR environment, this left Drupal in a state where attempting to run Awestruct against the instance failed. The concern here being that when changes are made to the production instance, the synchronisation process would take the production instance offline. References to this kind of behaviour as Drupal 8 bug reports can be found: * https://www.drupal.org/node/2638392 * https://www.drupal.org/node/2583113 *Definition of Done* # Users cannot break the Drupal configuration synchronisation process by creating custom shortcut lists | Creation of custom shortcut lists causes Drupal start-up to fail | 2017-01-31 08:46 | 1
733369 | 12673767 | Story | All blog posts and pages at the previous blog need to have redirect rules applied to ensure that a visit to the blog post will redirect user to the same post at the new blog location. For now, this can be done via the Safe Redirect Manager within the VIP-based blog but once we deactivate that a server redirect of some sort will have to be implemented. | Redirect previous blog post links to their location in newer blog | 2017-01-30 14:46 | 201
733581 | 12659519 | Story | We need a feature (e.g 'trash can') for finding pages that were mistakenly deleted. The Super Admin can empty the trash whenever. cc [~lincolnthree] h2. Definition of Done # Pages that were mistakenly deleted can be found. # Pages that were mistakenly deleted can be restored. | Need drupal "trash can" to retrieve deleted pages/docs | 2016-11-04 10:16 | 666
733647 | 12653390 | Story | Currently /downloads makes many REST API calls. It looks to be one per download link on the page. Also, the response to these requests returns multiple versions for the product, which is unnecessary. There is a single API call that can pull all the information needed by the entire page: https://developers.redhat.com/download-manager/rest/available/rhel,eap,devstudio,fuse,datagrid,eap,webserver,cdk,devsuite,amq,brms,bpmsuite,datavirt,mobileplatform,openshift,openjdk,dotnet?nv=1 Note the list of product codes in the request. Ideally that list would be loaded from wherever the page is currently configured, rather than being hard-coded. Note: 'nv=1' states that only the latest version should be returned for each product. *Componentizing Search Page* Create a new JS component for controlling the search page. h2. Definition of done # The /downloads page only makes one REST API call on the download manager # All the download links continue to work\ # The version numbers continue to display against each download. | Improve the performance of /downloads | 2016-10-05 08:54 | 201
735846 | 12592554 | Epic | h2. Requirements * See: https://docs.google.com/document/d/1rn61zVnsXFc_C5F4kdr8VMRi_scpTWUatGIZPgWdc70/edit# * In particular, see the following for MVP tasks: https://docs.google.com/document/d/1rn61zVnsXFc_C5F4kdr8VMRi_scpTWUatGIZPgWdc70/edit#heading=h.ty3lqprumimi h2. Team UX: [~tnolan@redhat.com] Engineering: [~ldary24] Engineering support: [~akandel@redhat.com] (If we use Adobe Target) Marketing: [~mguerett] Visual Design: [~jcobb@redhat.com] | Site Outage - User Messaging Improvements (MVP) | 2015-11-12 08:54 | 745